ULL INDIA

United Learning League · Inspiring Generations

Master Plan

Website, CMS, Admissions CRM, Visitor Management, Family Dashboards, Marketing and AI Operations

ULL Auremont (CBSE)  ·  ULL Global (IB)

Campus: ULL Auremont School, Nagarbhavi, Bengaluru, Karnataka

| Document | Master plan for client review |
| --- | --- |
| Version | 1.0 (draft for review) |
| Date | 23 October 2026 |
| Planning window | 26 Oct 2026 to 30 Apr 2027 |
| Status | For discussion. Dates, scope and costs to be confirmed with ULL India |

# Contents

Executive summary

1. Timeline for all workstreams

2. AWS deployment (infra, CDK, domain, DNS, SSL, CDN, backups)

3. GST, company profile and payment details

4. Marketing, online and offline

5. Brand architecture (ULL India, ULL Global, ULL Auremont)

6. Visitor management dashboard and operational intelligence

7. Website with CMS, AI content intake and SEO validation

8. In-house CRM for group admins, school admins and counsellors

9. SSO for admins (Microsoft Entra ID) and for parents and students

10. Student dashboard

11. Parent dashboard

12. Google Business Profile connector in the admin portal

13. CDN for all media uploads and references

14. Social media and metrics dashboard for the group admin

15. Competitor deep study and gap report

16. Dedicated pages for ULL Global and ULL Auremont

17. Success metrics for each team

18. CRM lead source attribution (online, offline, coupons, WhatsApp)

19. External CRM sync (Orggen CRM / Zoho CRM)

20. ULL India on aptitudetest.in (ullindia.aptitudetest.in)

21. Audio recorder devices and AI success metrics per persona

22. Sarvam AI voice agents (outbound and common inbound with human handover)

Appendix A. Decisions needed from ULL India

Appendix B. Glossary

# Executive summary

This document brings together the plans for every workstream ULL India asked for: one umbrella website with dedicated sections for ULL Auremont and ULL Global, an AI-assisted CMS, an in-house admissions CRM, visitor management at the campus gate, sign-in for staff and families, student and parent dashboards, psychometric assessments, marketing, success metrics and AI-driven operations. Each of the 22 sections can be reviewed and approved on its own.

## Where ULL India stands today

| Brand | Curriculum | Status |
| --- | --- | --- |
| ULL India | Umbrella brand | Group website at ullindia.com |
| ULL Auremont | CBSE, Nursery to Grade 10 | Live campus: ULL Auremont School, Nagarbhavi, Bengaluru |
| ULL Global | IB | Brand defined; no campus yet (launching, with a waitlist) |

Already built: separate UAT and production environments on AWS (Mumbai region), a fast static website with a visual page builder, the CMS at /admin with staff roles, a first version of the Admissions & Visitor Desk for enquiries and visit requests, email/SMS/WhatsApp notifications, and media served from a CDN.

## What we will deliver

| Area | Sections | Outcome |
| --- | --- | --- |
| Foundations | 2, 3, 13 | Secure AWS hosting on ullindia.com with SSL, CDN and tested backups; legal entity, GST and payment gateway set up |
| Brand and website | 5, 7, 15, 16 | One umbrella site with /auremont and /global sections, based on the competitor study and gap report; the content team publishes AI-assisted pages that must pass SEO checks first |
| Admissions engine | 6, 8, 18, 19 | Every lead captured with its source (online, offline, coupon, WhatsApp), managed in the in-house CRM, mirrored to Zoho or Orggen, and followed through to the campus visit |
| Families and learning | 9, 10, 11, 20 | Microsoft sign-in for staff; phone OTP sign-in for families; student and parent dashboards with weekly reports; psychometric tests on ullindia.aptitudetest.in |
| Growth | 4, 12, 14, 17 | Online and offline marketing, a Google Business Profile connector, a social and ads metrics dashboard, and success metrics for every team |
| AI operations | 21, 22 | Conversation recording with AI scorecards per persona; Sarvam AI voice agents for outbound calls and a common inbound number, with handover to staff |

## Phases and key dates

| Phase | Window | Goal |
| --- | --- | --- |
| P0 Foundation | 26 Oct – 13 Nov 2026 | Production live on ullindia.com, legal details, competitor study, success metrics agreed |
| P1 Launch | 9 Nov – 18 Dec 2026 | Umbrella website with Auremont and Global sections, AI-assisted CMS, CRM with source tracking, marketing live. Launch: Monday 14 December 2026 |
| P2 Operate | 4 Jan – 26 Feb 2027 | Visitor desk pilot at Nagarbhavi, external CRM sync, Google Business Profile, social dashboard, family sign-in, aptitude tests, recorder pilot |
| P3 Automate | 1 Feb – 26 Mar 2027 | Voice agents, AI follow-ups, conversation analytics |
| P4 Learn | 1 Feb – 30 Apr 2027 | Student and parent dashboards ready for the 2027-28 academic year |

Why this order: competitors are already taking 2027-28 admissions, and most families shortlist schools between November and February. The website, lead capture and CRM therefore go live together before mid-December. Everything after that can move without affecting the admissions season.

## Key recommendations

- One domain, brand folders: ullindia.com/auremont and ullindia.com/global, with the subdomains redirecting there. This concentrates SEO strength. Ryan Group shows the cost of mixing paths, subdomains and separate domains.

- ULL Global before a campus: "launching soon" pages and a register-interest form. Wording follows IB rules until authorisation.

- Phone OTP and WhatsApp-first communication: none of the three competitors studied verifies phone numbers or offers instant WhatsApp. This is ULL's clearest advantage in lead quality and response speed.

- Consent by design: parent profile enrichment, conversation recording and children's data all follow India's DPDP Act. Every one of them needs stored consent, a stated purpose and a fixed retention period.

- Psychometric tests: MMPI is a clinical tool that needs a qualified psychologist. DMIT (fingerprint-based) lacks scientific support. ULL leadership should decide whether either is offered under the ULL brand.

- Alumni videos: ULL Auremont is new, so "founding family" and parent stories take the place of alumni stories for this season.

## What we need from ULL India

Appendix A lists every open decision in one place, grouped by section. The ones that block the December launch are: domain registrar access, the legal entity and GST details, school content (story, facilities, fees, faculty, real photos), the marketing budget and seat targets, and the Microsoft 365 tenant admin for staff sign-in.

# 1. Timeline for all workstreams

One delivery calendar for the 22 workstreams, starting Monday 26 Oct 2026. Built around the 2027-28 admissions season (peak Nov–Mar) and the 2027-28 academic year (Apr–Jun 2027). Each workstream has its own section in this document; this section sets order, dates, dependencies and owners.

### Key actions

- Confirm the start date (26 Oct 2026) and the website launch date (Mon 14 Dec 2026)

- Name one owner per workstream (tech, content, marketing, sales, school ops)

- Start vendor paperwork in week 1 (Zoho/Orggen, Sarvam, WATI, Gupshup, Apollo, Google Business Profile API access, Meta Business verification)

- Run a 30-minute weekly review every Friday against this calendar and the success metrics in section 17

## Assumptions

- Start: Monday 26 Oct 2026. Dates are week-start Mondays.

- Team: 2 full-stack developers, 1 designer (part-time), 1 content lead + AI tools, 1 digital marketer, 1 social/video person, ground sales at Nagarbhavi. If the team is smaller, phases 3–4 slip and phases 1–2 stay.

- Season: 2027-28 admissions are already open across competitors (VIBGYOR's form defaults to 2027-28, Orchids advertises "Admissions 2027-28"). The site, lead capture and CRM must be live before mid-December, because Nov–Feb is when most families shortlist schools.

- Holidays: Diwali falls around 8 Nov 2026 (expect a slow week), Christmas/New Year (21 Dec–1 Jan, reduced team).

- What exists today: UAT and prod CDK stacks, a static Next.js site with a page builder, Payload CMS with Pages, Media, Enquiries and Users, roles, SES/Gupshup/WATI notification adapter, and versioned CDN uploads.

## Phases

| Phase | Window | Goal |
| --- | --- | --- |
| P0 Foundation | 26 Oct – 13 Nov | Prod live on ullindia.com, legal and company details settled, competitor study done, metrics agreed |
| P1 Launch | 9 Nov – 18 Dec | Umbrella site with Auremont + Global sections, AI-assisted CMS, CRM v1 with source tracking, marketing live |
| P2 Operate | 4 Jan – 26 Feb | Visitor desk at Nagarbhavi, external CRM sync, GBP connector, social dashboard, family SSO, aptitude tests, recorder pilot |
| P3 Automate | 1 Feb – 26 Mar | Voice agents, AI follow-ups, conversation analytics at scale |
| P4 Learn | 1 Feb – 30 Apr | Student and parent dashboards, ready for the 2027-28 academic year |

## Calendar by workstream

| # | Workstream | Start | End | Depends on | Milestone |
| --- | --- | --- | --- | --- | --- |
| 02 | AWS deployment (infra, CDK, domain, DNS, SSL, CDN, backups) | 26 Oct | 13 Nov | AWS account (done) | ullindia.com served from prod, restore drill passed |
| 03 | GST, company profile, payment details | 26 Oct | 20 Nov | Company documents from finance | Legal footer live, gateway KYC submitted |
| 04 | Marketing (online + offline) | 2 Nov | ongoing | 05, 15, 17 | Campaigns live 14 Dec, campus walkthrough video by 11 Dec |
| 05 | Brand architecture (ULL India → ULL Global, ULL Auremont) | 26 Oct | 6 Nov | Brand assets | Naming, URL map and logo rules signed off |
| 06 | Visitor management + operational intelligence | 30 Nov | 29 Jan | 08, 09 | Gate QR + OTP pilot at Nagarbhavi 18 Jan |
| 07 | Website CMS with AI content + SEO validation | 2 Nov | 11 Dec | 13 | Content team publishes without developers |
| 08 | In-house CRM at /admin | 9 Nov | 18 Dec | 09 (staff SSO optional for v1) | Pipeline board live at site launch |
| 09 | SSO: staff (Entra ID) + parent/student | 2 Nov (staff) / 4 Jan (families) | 20 Nov / 29 Jan | Microsoft 365 tenant admin | Staff sign in with Microsoft by 20 Nov |
| 10 | Student dashboard | 1 Feb | 9 Apr | 09, 20, school ERP data | Beta for one grade band 9 Apr |
| 11 | Parent dashboard | 15 Feb | 23 Apr | 10 | First weekly report sent 23 Apr |
| 12 | Google Business Profile connector | 4 Jan | 22 Jan | GBP API approval (apply in week 1) | Reviews and posts managed from /admin |
| 13 | CDN for all uploads | 26 Oct | 6 Nov | 02 | Every upload and site asset served from cdn.ullindia.com |
| 14 | Social media metrics for group admin | 11 Jan | 5 Feb | Meta, YouTube, LinkedIn access | Weekly dashboard in /admin |
| 15 | Competitor deep study + gap report | 26 Oct | 6 Nov | none | Gap report and must-have list signed off |
| 16 | Dedicated pages for ULL Global and ULL Auremont | 9 Nov | 11 Dec | 05, 07, 15, content from school | Both sections live 14 Dec |
| 17 | Success metrics for each team | 2 Nov | 13 Nov | 15 | Targets agreed; dashboard from 14 Dec |
| 18 | CRM lead source attribution (online, offline, coupon, WhatsApp) | 16 Nov | 18 Dec | 08 | Every lead has a source at launch |
| 19 | External CRM sync (Orggen / Zoho) | 4 Jan | 22 Jan | 08, 18, vendor API docs | Leads mirrored within 1 minute |
| 20 | ullindia.aptitudetest.in psychometric integration | 11 Jan | 19 Feb | 09, integration docs | Test status and reports in both dashboards |
| 21 | Audio recorder devices + AI success metrics | 18 Jan | 26 Feb | 06, 08, device purchase | Scorecards for 4 personas |
| 22 | Sarvam AI voice agents (inbound + outbound) | 1 Feb | 26 Mar | 08, 19, telecom DLT | Fee reminders and inbound desk live |

## Gantt

## Critical path

02 → 13 → 07 → 16 → launch 14 Dec. The CRM (08 + 18) must be ready the same day, because ads (04) start driving leads at launch. Anything in P2–P4 can move without affecting the season.

## Things to start in week 1, because other people take time

- Google Business Profile API access request (approval can take weeks).

- Meta Business Manager verification and WhatsApp Business (WATI) template approval.

- DLT registration for SMS and voice (TRAI) under the company entity; needed before 06, 22.

- Microsoft Entra ID app registration by the tenant admin (09).

- Brainwonders / aptitudetest.in integration docs and subdomain setup (20).

- Orggen / Zoho API credentials and field list (19).

- Sarvam AI account, telephony partner and pricing (22).

## Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| School content (photos, fees, facilities, faculty) arrives late | 16 slips past the launch | Launch with what we have; mark pages "coming soon" rather than delay the site |
| ULL Global has no campus yet | Thin pages, weak SEO | Position as "launching" with an interest/waitlist form (section 5/16) |
| Vendor approvals (GBP, Meta, DLT) | 12, 14, 22 slip | Apply in week 1; build against sandbox/dry-run modes |
| Recording and enrichment consent (DPDP Act) | Legal exposure | Consent screens and retention rules designed in 06/21 before any pilot |
| One EC2 per stage grows into CRM + jobs | Performance | Section 2 adds a job queue and an RDS path before P2 |

# 2. AWS deployment (infra, CDK, domain, DNS, SSL, CDN, backups)

Finish and harden what the CDK app in infra/ already creates for UAT and prod. Attach ullindia.com, issue certificates, add a private documents bucket, monitoring, WAF and tested backups, and leave room for the CRM, VMS and AI jobs that come later. 26 Oct – 13 Nov 2026.

### Key actions

- Release the completed infrastructure, deploy and storage work to UAT, then to production

- Point ullindia.com at the Route 53 nameservers output by UllShared, or add records at the current registrar

- Deploy with -c attachDomains=true so the us-east-1 certificate stacks issue and CloudFront serves the real hostnames

- Add SES DKIM, SPF, DMARC and a custom MAIL FROM; request SES production access

- Add a private documents bucket per stage (applicant documents, call recordings, reports) with signed URLs only

- Nightly pg_dump via a systemd timer, daily EBS snapshots via AWS Backup, 30/90-day retention, cross-region copy for prod, and a monthly restore drill

- CloudWatch agent, alarms (CPU, disk, memory, 5xx, health check), SNS to email/Teams, AWS Budgets alerts

- AWS WAF on the site distribution with rate limits on /api/enquiries and OTP endpoints, and managed rule groups

- Add an SQS queue and a worker container for slow jobs (enrichment, transcription, CRM sync, voice calls)

- Write deploy/RUNBOOK.md covering deploy, rollback, restore and secret rotation

## What already exists (in infra/)

| Stack | Region | Contents |
| --- | --- | --- |
| UllShared | ap-south-1 | Route 53 public zone ullindia.com, GitHub OIDC provider |
| UllUat / UllProd | ap-south-1 | Site bucket, versioned media bucket, backup bucket (30-day expiry), ECR repo, Secrets Manager (Payload, Postgres, hook), EC2 t3.medium with Elastic IP and SSM, site CloudFront (S3 + /api /admin to EC2), CDN CloudFront (immutable, 1 year), Route 53 A/AAAA, GitHub deploy role |
| UllUatCert / UllProdCert | us-east-1 | ACM certificate, created only with -c attachDomains=true |

Hostnames: uat.ullindia.com, cdn-uat.ullindia.com, ullindia.com, www.ullindia.com, cdn.ullindia.com.

## Target picture (after this plan)

## 1. Domain and DNS

- Find out where ullindia.com is registered and who controls it (GoDaddy, Hostinger etc.). Record it in the runbook.

- Recommended: delegate the whole domain to Route 53 (copy the four NameServers from the UllShared output to the registrar). CDK then owns every record.

- If email (Google Workspace / Microsoft 365) already runs on the domain, copy its MX, SPF, DKIM, autodiscover and verification TXT records into the Route 53 zone before switching nameservers. Add them to shared-stack.ts so they are in code.

- Lower the TTL at the old provider to 300s two days before the switch.

- Future subdomains reserved now (section 5): auremont.ullindia.com and global.ullindia.com as 301 redirects to /auremont and /global; portal.ullindia.com optional; ullindia.aptitudetest.in is owned by aptitudetest.in, not us (section 20).

## 2. SSL

- ACM certificate in us-east-1 per stage (already coded). Add the redirect hostnames (auremont.ullindia.com, global.ullindia.com) to the prod SANs.

- TLS 1.2 minimum (already set). Add an HSTS response header policy (max-age=31536000; includeSubDomains) only after the domain has been stable for a week.

- ACM renews automatically while the DNS validation records stay in place. Keep them.

## 3. CDN

Covered in detail in section 13. Infra items here: the CDN distribution, cache policy, and an S3 lifecycle rule that moves non-current media versions to Glacier Instant Retrieval after 90 days.

## 4. Private documents bucket (new)

For applicant documents, call recordings (section 21), psychometric reports (section 20) and exported reports.

- BlockPublicAccess.BLOCK_ALL, SSE-KMS with a stage key, versioning on, no CloudFront.

- Access only through short-lived presigned URLs (5 minutes) generated by Payload after an access check.

- Lifecycle: recordings 180 days then delete (configurable, see section 21); applicant documents kept until the admission year closes + 1 year.

- Instance role gets s3:GetObject/PutObject on this bucket only.

## 5. Backups and restore

| What | How | Retention | Where |
| --- | --- | --- | --- |
| Postgres logical dump | deploy/backup-db.sh on a systemd timer at 02:00 IST (today it is a cron comment only) | 30 days UAT, 90 days prod | Backup bucket |
| EBS volume | AWS Backup plan, daily | 7 daily + 4 weekly | AWS Backup vault |
| Prod dumps off-region | S3 replication to ap-south-2 (Hyderabad) | 90 days | DR bucket |
| Media | S3 versioning (already on) | Non-current to Glacier IR after 90 days | Media bucket |
| Code + infra | Git + ECR (last 10 images) | Forever / 10 | GitHub, ECR |

- Add a "backup succeeded" metric; alarm if no new object in 26 hours.

- Monthly restore drill: restore the latest dump into a throwaway container, run payload migrate:status, count rows in enquiries, record the time it took. Target RPO 24h, RTO 2h.

## 6. Monitoring and cost

- CloudWatch agent on EC2 for memory and disk. Alarms: CPU > 80% 10 min, memory > 85%, disk > 80%, status check failed, CloudFront 5xx > 2%, Route 53 health check on /api/health (add this endpoint).

- SNS topic → email to tech owner + Microsoft Teams webhook.

- AWS Budgets: alert at 80% and 100% of a monthly budget (start at $150 for both stages; current running estimate is about $90–110 per month).

- Log retention: 30 days.

## 7. Security

- WAF on the site distribution: AWS managed common + known bad inputs + IP reputation; rate-based rule 100 requests / 5 min per IP on /api/enquiries*, /api/otp*, /api/visits*.

- Rotate the Payload and hook secrets once after launch; document the rotation.

- No SSH; SSM Session Manager only (already).

- Enable GuardDuty and AWS Config basic rules in prod (low cost, one-time setup).

## 8. Room for what comes next

| Need | When | Change |
| --- | --- | --- |
| Slow jobs (Apollo enrichment, transcription, CRM sync, voice call orchestration) | P2 | SQS queue + worker service in docker-compose.aws.yml on the same EC2 |
| More load from CRM + dashboards | When DB > 20 GB or CPU stays > 60% | Move Postgres to RDS (db.t4g.medium, Multi-AZ for prod), keep EC2 for Payload |
| Webhooks from WATI, Meta Lead Ads, Sarvam, aptitudetest.in | P1–P3 | /api/hooks/* routes behind CloudFront, verified by HMAC signature, excluded from caching |
| Family portal on a subdomain (if chosen) | P2 | Extra alias on the site distribution, same certificate |

## Acceptance

- https://ullindia.com, https://www.ullindia.com and https://cdn.ullindia.com serve over valid TLS; http redirects to https.

- SES out of the sandbox; enquiry email lands in Gmail inbox with DKIM pass.

- A restore drill completed and logged.

- Alarms fire into email/Teams in a test.

- deploy/RUNBOOK.md reviewed by a second person.

## Open questions

- Who is the registrar and who holds the login?

- Is email already on the domain (Google Workspace or Microsoft 365)? Microsoft 365 is likely if Entra ID SSO is wanted (section 9).

- Is a Hyderabad DR copy wanted for prod, or is same-region versioning enough?

# 3. GST, company profile and payment details

Collect the legal entity details for ULL India and each school, show them correctly on the website and invoices, set up a payment gateway for fees and paid services, and make sure AWS and other vendors bill the right GSTIN. 26 Oct – 20 Nov 2026.

### Key actions

- Confirm which legal entity (company or trust/society) runs ULL India, ULL Auremont and ULL Global, with CIN/registration, PAN, GSTIN and registered address

- Ask the CA which ULL services are GST-exempt (school tuition) and which are taxable (psychometric tests, events, merchandise, third-party services)

- Add a Legal Entities collection in Payload and show the right entity in each school's footer, contact page and invoices

- Publish Privacy Policy (DPDP Act aligned), Terms, Refund & Cancellation, Fee Policy and Grievance Officer pages

- Choose a payment gateway (Razorpay recommended), submit KYC, connect settlement bank accounts per entity

- Add the GSTIN to AWS, Google, Meta, Zoho, Sarvam and other vendor billing so input tax credit can be claimed

Not tax or legal advice. Every GST rate and exemption below must be confirmed by ULL's CA before it goes into invoices.

## 1. Company profile to collect

One row per legal entity. Schools in India are often run by a trust or society, while marketing, tech or test services may sit in a private limited company.

| Field | ULL India (group) | ULL Auremont School | ULL Global |
| --- | --- | --- | --- |
| Legal name |  |  |  |
| Type (Pvt Ltd / Trust / Society / LLP) |  |  |  |
| CIN or registration number |  |  |  |
| PAN |  |  |  |
| GSTIN (if registered) |  |  |  |
| Registered address with PIN |  |  |  |
| Campus address (if different) |  | Nagarbhavi, Bengaluru 5600xx | not yet |
| Board affiliation number | – | CBSE affiliation no. (or "applied for") | IB school code (or "candidate / interested") |
| UDISE+ code | – |  |  |
| Authorised signatory |  |  |  |
| Grievance officer (DPDP) name, email |  |  |  |
| Bank account for settlement |  |  |  |

Where it goes in the product

- New Payload collection legalEntities (admin only) and a legalEntity relation on each School (section 5).

- Website footer per school: legal name, address, affiliation number, "CBSE Affiliation No. xxxx". CBSE requires schools to publish mandatory public disclosure details on their site; add a /auremont/mandatory-disclosure page (section 16).

- Invoices and receipts (fees, test reports) print the entity, GSTIN and address.

- Structured data: School JSON-LD gets legalName, address, telephone, identifier (affiliation).

## 2. GST questions for the CA

| Item | Likely treatment to confirm |
| --- | --- |
| School tuition, admission fee, exam fee (pre-school to higher secondary) | Exempt as services by an educational institution to its students |
| Transport, mid-day meals, security, housekeeping bought by the school | Vendor-side exemptions may apply up to higher secondary |
| Psychometric tests / career counselling sold to outsiders (section 20) | Likely taxable (commonly 18%); check if sold by the school or a separate entity |
| Summer camps, events open to the public, merchandise, uniforms, books | Check each; uniforms/books have their own rates |
| Registration / application fee | Check whether it counts as admission-related |
| Advertising, SaaS and AWS bills received by ULL | Taxable; claim input credit only where the receiving entity makes taxable supplies |

Output: a one-page "tax matrix" from the CA, which the payment module uses to decide whether to add GST to a line item.

## 3. Payment gateway

Recommended: Razorpay (wide use in Indian schools, UPI/cards/net-banking/EMI, Payment Links, Smart Collect virtual accounts, subscriptions, good webhooks). Alternatives: PayU, Cashfree, CCAvenue. Pick one; keep the code behind a payments adapter like cms/src/lib/notify.ts.

| Use case | When | Gateway feature |
| --- | --- | --- |
| Registration / application fee (currently not charged) | Optional for 2027-28 | Checkout on the portal |
| Admission confirmation deposit | P2 | Payment Link sent from CRM |
| Term fees with reminders (voice agent, section 22) | P3 | Payment Links / UPI AutoPay |
| Paid psychometric tests (section 20) | P2 | Handled by aptitudetest.in or ULL's gateway (decide) |

KYC documents usually needed: entity PAN, registration certificate/trust deed, GST certificate (if any), cancelled cheque, authorised signatory ID, website with legal pages live. The legal pages must be live before KYC is approved, so they are part of the website launch.

Payment data in our database: order id, amount, status, gateway reference, receipt number. Never card or UPI details. Webhooks at /api/hooks/payments with signature verification.

## 4. Legal pages (website)

- Privacy Policy aligned to the Digital Personal Data Protection Act 2023 and its Rules: what we collect (enquiries, visitor registration, call recordings, LinkedIn/Apollo enrichment, children's data), purpose, retention, rights, grievance officer, consent withdrawal.

- Children's data: the dashboards (sections 10, 11) process data of students under 18. This needs verifiable parental consent and no tracking or targeted ads aimed at children.

- Terms of Use, Refund & Cancellation, Fee Policy, Cookie Policy (consent banner, section 7).

- Each page is a CMS page so legal can update it without a deploy.

## 5. Vendor billing with GSTIN

| Vendor | Action |
| --- | --- |
| AWS (bills through Amazon Web Services India Pvt Ltd) | Add GSTIN and legal address in Billing → Tax settings |
| Google Workspace / Ads, Meta Ads | Add GSTIN in billing profile |
| Zoho / Orggen, WATI, Gupshup, Sarvam, Apollo | Ask for GST invoices to the right entity |

## Acceptance

- Entity table filled and signed off by finance.

- Footer and contact pages show correct legal details for each school.

- Legal pages live on prod.

- Gateway account approved with test-mode payments working in UAT.

- CA's tax matrix stored in the project drive and linked here.

## Open questions

- Which entity collects school fees today, and through which bank or gateway?

- Does ULL want online fee collection in 2027-28, or only lead capture this season?

- Is a registration fee planned for 2027-28 admissions?

# 4. Marketing, online and offline

A season plan for the 2027-28 admissions cycle covering brand presence, social media, digital ads (Meta, Google, YouTube), video (campus walkthrough, parent and alumni stories, event aftermovies), the gallery, and offline activity around Nagarbhavi. Every channel feeds tracked leads into the CRM (section 18). 2 Nov 2026 onward, peak Dec–Mar.

### Key actions

- Write one positioning line and three proof points each for ULL India, ULL Auremont and ULL Global

- Shoot the campus walkthrough, a 60s brand film, 6 parent/teacher stories and a photo library before 11 Dec

- Set up or claim Instagram, Facebook, YouTube, LinkedIn and Google Business Profile for each brand, all owned by a company Business Manager

- Install GA4, Meta Pixel + Conversions API, Google Ads conversion tags, and the UTM convention before any spend

- Launch Meta (lead + traffic) and Google Search campaigns on 14 Dec with the budget split below

- Book offline activations near Nagarbhavi (societies, preschools, hoardings, events) with unique QR codes and coupon codes

- Publish a 12-week content calendar and review it weekly against section 17

## Goal for the season

Fill the 2027-28 intake at ULL Auremont (Nursery to Grade 10, CBSE) and build a waitlist for ULL Global (IB). Everything is measured as campus visits booked and admissions confirmed, not likes.

## 1. Brand presence (foundations, Nov)

| Item | ULL India | ULL Auremont | ULL Global |
| --- | --- | --- | --- |
| Website section | ullindia.com | ullindia.com/auremont | ullindia.com/global |
| Instagram | @ullindia | @ullauremont | @ullglobal (reserve now) |
| Facebook page | yes | yes | reserve |
| YouTube | one channel, playlists per school |  |  |
| LinkedIn | company page (hiring, leadership, partnerships) | showcase page | showcase page |
| Google Business Profile | – | Nagarbhavi campus (section 12) | when a campus exists |
| WhatsApp Business | one number per school via WATI |  |  |
| Listings | Edustoke, SchoolMyKids, Justdial, Sulekha, Google Maps |  |  |

Keep name, address and phone identical everywhere (local SEO).

## 2. Content pillars

- Learning that shows: the Learning Cycle, classroom moments, Aurora Lab and robotics, project work.

- Sport and fitness: the Jonty Rhodes association, coaching, sports week.

- Beyond the classroom: Pulse, Ruchi, Kushala, Summit Pathway.

- Safety and care: CCTV, transport, nurse, counsellor, teacher-student ratio. Competitors (VIBGYOR) put safety on the homepage; parents ask about it first.

- People: teachers, the principal, parents' stories.

- Results and recognition: as they arrive (Auremont is new, so lead with teacher credentials and partnerships rather than toppers).

## 3. Video plan

| Video | Length | Use | When |
| --- | --- | --- | --- |
| Campus walkthrough (gimbal + drone) | 2–3 min + 30s cut | Website hero, YouTube, Google Business Profile, WhatsApp follow-up | by 11 Dec |
| Brand film "Rooted deep. Rising high." | 60s + 15s + 6s bumpers | YouTube ads, Meta Reels | by 11 Dec |
| Principal's welcome | 90s | Admissions page, follow-up messages | by 11 Dec |
| Parent stories | 6 × 45s | Reels, Shorts, testimonials block | Dec–Jan |
| Teacher spotlights | 6 × 30s | Social, "our teachers" page | Jan |
| A day at ULL Auremont | 90s | Social, portal | Jan |
| Event aftermovies (sports day, annual day, Pulse) | 60–90s within 72 hours of each event | Social, gallery, alumni/parent groups | each event |
| Alumni stories | 60s | Brand recall | Auremont is a new school with no alumni yet. Use ULL leadership's previous schools, or switch this to "founding family" stories |
| ULL Global explainer (IB approach) | 90s animated | Global page, waitlist ads | Jan |

Every video gets: captions (English + Kannada subtitles for Reels), a vertical cut, and a CTA to book a visit with a tracked link.

## 4. Gallery

- CMS gallery (existing gallery block) with albums: Campus, Classrooms, Sports, Events, Labs. Filters on the Campus page.

- Upload rules: real photos only (the concept site uses AI visuals; replace them before launch), alt text required, faces of children only with photo consent recorded.

- Event albums published within 48 hours of the event, linked from the aftermovie.

## 5. Digital paid media

Starting monthly split (adjust after 4 weeks of data):

| Channel | Share | Objective | Notes |
| --- | --- | --- | --- |
| Google Search | 35% | Visits booked | Keywords: "CBSE school Nagarbhavi", "best school near Vijayanagar", "school admission 2027-28 Bengaluru", competitor-adjacent terms; geo 8–10 km radius |
| Meta (Instagram + Facebook) | 35% | Leads + visits | Instant Forms with a qualifying question (grade), plus traffic to the visit page; parents 26–45, 8 km radius |
| YouTube | 15% | Reach + recall | In-stream skippable with the 15s/60s films; retarget site visitors |
| Performance Max / Discovery | 10% | Extra reach | Only after conversions are tracked |
| Retargeting | 5% | Return visitors | Website visitors who did not book |

Rules:

- Every ad URL uses the UTM convention from section 18 (utm_source, utm_medium, utm_campaign, utm_content).

- Meta Lead Ads and Google lead forms post straight into the CRM via webhooks (section 18), so leads are called in minutes.

- Conversion events: enquiry_submitted, visit_booked, visit_attended (offline conversion upload from the CRM).

## 6. Organic social cadence

| Platform | Frequency | Format |
| --- | --- | --- |
| Instagram | 5 posts + daily stories | 3 Reels, 2 carousels |
| Facebook | 3 posts | Cross-post + parent community events |
| YouTube | 1 long + 3 Shorts | Walkthrough, stories |
| LinkedIn | 2 posts | Leadership, hiring, partnerships |
| Google Business Profile | 1 post | Events and offers (section 12) |

## 7. Offline marketing (Nagarbhavi and around)

| Activity | Tracking |
| --- | --- |
| Hoardings and bus-shelter ads on main roads (Nagarbhavi, Vijayanagar, Rajarajeshwari Nagar, Chandra Layout) | Unique QR → /auremont/visit?src=hoarding-<id> |
| Apartment society activations (weekend stalls, kids' activity) | QR + coupon code per society |
| Preschool tie-ups (Grade 1 feeders) | Referral code per preschool |
| Open houses and campus tours every Saturday | Visit bookings in CRM |
| Workshops (parenting, robotics, sports clinic with coaches) | Event registration form |
| Newspaper inserts / pamphlets in local editions | QR + call-tracking number |
| Parent referral programme | Referral code per family |
| Brochure (print + PDF) | QR on back page |
| Radio / cinema (optional, if budget) | Vanity URL |

Ground sales team logs every walk-in in the visitor desk (section 6) so offline is measured too.

## 8. Season calendar

| Weeks | Focus |
| --- | --- |
| 2 Nov – 13 Dec | Shoot, accounts, tracking, listings, brochure, hoarding booking |
| 14 Dec – 10 Jan | Launch: paid + organic, open houses every Saturday |
| 11 Jan – 28 Feb | Peak: workshops, society activations, referral push |
| Mar | Last-seat urgency, admission confirmed stories |
| Apr–Jun | Orientation content, first-day aftermovie, ULL Global waitlist |

## Acceptance

- All accounts owned by the company, not personal profiles.

- Tracking verified with test leads from every channel before spend.

- Walkthrough and brand film live by 14 Dec.

- Weekly report (section 17) from week 1 of spend.

## Open questions

- Monthly media budget for Dec–Mar?

- Is the Jonty Rhodes association cleared for ads (image rights, duration)?

- Does ULL Global have a launch year and city yet?

# 5. Brand architecture (ULL India, ULL Global, ULL Auremont)

Model ULL India as the umbrella brand with two school brands, ULL Global (IB) and ULL Auremont (CBSE), and one physical campus today (ULL Auremont School, Nagarbhavi, Bengaluru). Make the CMS, URLs, roles and data multi-brand and multi-campus so future schools and initiatives drop in without code changes. 26 Oct – 6 Nov 2026.

### Key actions

- Sign off names, taglines, logo lockups and colour per brand

- Add Brands and Campuses collections in Payload; relate Pages, Media, Enquiries and Users to them

- Adopt /auremont and /global paths with subdomain redirects

- Scope School admin, counsellor and front desk users to one or more campuses

- Decide how ULL Global is presented before it has a campus (launching soon + interest form)

## Today

| Level | Name | Curriculum | Physical presence |
| --- | --- | --- | --- |
| Group (umbrella) | ULL India (United Learning League, "Inspiring Generations") | – | – |
| School brand | ULL Auremont | CBSE, Nursery – Grade 10 | ULL Auremont School, Nagarbhavi, Bengaluru, Karnataka (only campus today) |
| School brand | ULL Global | IB | none yet |
| Future | other initiatives (preschool, sports academy, aptitude/career services, teacher academy) | – | – |

The logo lockup in content/brand/ull-logo-lockup.jpg already shows "ULL Global · ULL Auremont". Brand colours from PLAN.md 2a: navy primary for all, orange accent for Auremont, teal accent for Global, gold for rules and badges.

## Model: brand → campus

A brand is what parents choose (curriculum, philosophy). A campus is where the child goes. Leads, visits, staff and students belong to a campus; content belongs to a brand and optionally a campus.

## URL structure

Recommendation: subfolders, not subdomains.

| Option | Pros | Cons |
| --- | --- | --- |
| Subfolders ullindia.com/auremont, /global | One domain authority for SEO, one sitemap, one certificate, one login cookie, simpler analytics | – |
| Subdomains auremont.ullindia.com | Feels separate | Google treats each as its own site; splits authority; extra certs, cookies and analytics config |

Competitors: VIBGYOR uses paths (/school/{city}/{board}/{campus}), Orchids uses paths (/{city}-branches/{campus}), Ryan mixes paths, subdomains and separate domains. The mixed approach is the one to avoid (see section 15).

Final URL map:

ullindia.com/                         ULL India group home
ullindia.com/about, /leadership, /careers, /news, /contact
ullindia.com/auremont/                ULL Auremont brand home
ullindia.com/auremont/nagarbhavi/     campus page (address, map, transport, fees, visit)
ullindia.com/auremont/academics/...   brand-level content
ullindia.com/auremont/admissions/
ullindia.com/global/                  ULL Global brand home
ullindia.com/global/ib-programme/...
ullindia.com/global/interest/         waitlist until a campus opens
ullindia.com/initiatives/<name>/      future
auremont.ullindia.com  → 301 → ullindia.com/auremont/
global.ullindia.com    → 301 → ullindia.com/global/

The current site is built at the root (e.g. /academics/foundational). Move it under /auremont/ with 301 redirects from the old paths (redirects managed in CMS, section 7).

## CMS and data changes

New collections:

| Collection | Key fields |
| --- | --- |
| brands | name, slug (auremont, global), curriculum, tagline, accent colour, logo, legal entity (section 3), social links, status (live, launching, planned) |
| campuses | brand, name, slug (nagarbhavi), address, geo, phone, WhatsApp number, email, grades offered, affiliation no., Google Business Profile id (section 12), visiting hours, status |

Relations added to existing collections:

- pages.brand (optional = group page) and pages.campus (optional).

- media.brand for filtering the library.

- enquiries.brand + enquiries.campus (required; the form sets it from the page it is on).

- users.campuses (many) so a School admin, counsellor or front desk only sees their campus (update cms/src/access/roles.ts with row-level filters).

Site settings move from one global to per-brand values: header CTA labels, phone, WhatsApp, footer.

## Visual rules

- Group pages: navy + gold, ULL India lockup.

- Auremont pages: navy + orange accent, Auremont lockup, "a ULL India school" endorsement in the footer.

- Global pages: navy + teal accent, Global lockup, same endorsement.

- The header always shows the group switcher ("ULL India · Auremont · Global") so families can move between brands.

## How ULL Global appears before a campus exists

- Status launching: brand page, IB approach, leadership, "Register interest" form (creates a CRM lead with brand=global, intent=waitlist).

- No fees, no visit booking, no "admissions open" claims until IB authorisation status allows it. IB is strict about how candidate/authorised status is described; use only IB-approved wording.

## Acceptance

- Adding a third brand or second campus needs only CMS entries, no code.

- A counsellor assigned to Nagarbhavi cannot see a Global waitlist lead unless also assigned to Global.

- Old URLs redirect to /auremont/... with 301.

## Open questions

- Is ULL Global's first campus planned (city, year)? Is IB candidacy started?

- Should Auremont's campus page be /auremont/nagarbhavi now, even with one campus? (Recommended: yes, so a second campus needs no URL changes.)

- Final logo files (SVG) for each lockup.

# 6. Visitor management dashboard and operational intelligence

Gate registration with phone OTP, advance alerts to the counsellor and front desk, a parent profile enriched with Apollo (with consent), live visit statuses from entered_campus to left_campus, recording of the counselling conversation, and AI-driven follow-up over email, WhatsApp, SMS and voice. Extends the existing Enquiries collection. 30 Nov 2026 – 29 Jan 2027, pilot at Nagarbhavi from 18 Jan.

### Key actions

- Split visits out of Enquiries into a Visits collection with a status history

- Build the QR gate page with phone OTP (WhatsApp first, SMS fallback) and visit purpose

- Notify the assigned counsellor and front desk on pre-registration, arrival and long waits (web push, WhatsApp, Teams)

- Build the live "on campus now" board and visitor dashboard in /admin

- Add Apollo enrichment as a consented background job and a parent profile card for counsellors

- Link each counselling session to its recording, transcript and AI summary (device details in section 21)

- Generate and schedule follow-ups over email, WhatsApp, SMS and AI voice after each visit (voice details in section 22)

- Write the consent text and retention rules for OTP, enrichment and recording, reviewed against the DPDP Act

Reference product: Qudify's visitor management (QR check-in on the visitor's own phone, no app, WhatsApp approvals, digital passes, pre-invites, verification team, blacklist, logs, analytics, office-wise admin). We build the school version of this inside our CRM so a visit and an admission are one record.

## What exists

cms/src/collections/Enquiries.ts already stores type: visit, preferredDate and a visit.passCode, and notify() sends visit_requested, visit_confirmed and visitor_arrived templates. There is no gate page, OTP, status history or live board yet.

## A. Gate registration, alerts and parent profile

### Visitor journey

### Before arrival (pre-registration)

- Families who booked online get a WhatsApp/email message 24h and 2h before with their pass link. The pass QR encodes the visit id + pass code (already generated).

- The counsellor gets the day's schedule at 08:00 with each family's profile card.

- The front desk sees "expected today" on the board, and refreshments, a tour guide or a classroom observation slot can be prepared.

### At the gate

- One static QR poster at each entrance → ullindia.com/visit/checkin?campus=nagarbhavi&gate=main.

- Phone OTP: 6 digits, 5-minute expiry, 3 attempts, rate-limited by WAF (section 2). Send by WhatsApp authentication template (cheaper, higher delivery) with Gupshup SMS fallback. OTP templates need DLT registration for SMS.

- Visit purpose: admission enquiry, scheduled visit, parent of current student, vendor, interview candidate, other. Only admission purposes create CRM leads; others are logged as visitors.

- Optional tablet kiosk mode at the front desk for families without smartphones (same page, front-desk-assisted OTP).

- Guard verification view: scan the parent's pass to confirm; blacklist check (flagged numbers alert security).

### Visit statuses

| Status | Set by | Meaning |
| --- | --- | --- |
| pre_registered | Online booking | Slot booked, not arrived |
| entered_campus | Gate OTP success | Through the gate |
| in_campus | Front desk | Waiting in reception |
| with_counsellor | Counsellor taps "Start session" | Counselling started (starts recording, see B) |
| campus_tour | Counsellor / guide | Touring |
| child_interaction | Teacher | Child assessment / interaction |
| left_campus | Exit QR or guard | Visit complete |
| no_show | Auto at slot + 2h | Booked but did not come |
| cancelled | Parent / staff | Cancelled |

Each change is stored in visits.history[] with time and user, so we get wait time, session length and tour length per visit.

### Parent profile (operational intelligence)

Profile card shown to the counsellor before the parent sits down:

- From our data: child name and grade, source (section 18), pages viewed on the site, previous enquiries, calls, WhatsApp chats, siblings, current school, priority stated on the form.

- From enrichment (Apollo People Enrichment API by email/phone, or LinkedIn data via a licensed provider): job title, company, industry, seniority, city, LinkedIn URL.

- Derived: likely fee comfort band, relocation flag, distance from campus (from pincode), suggested talking points (generated by Claude from the above).

Compliance: scraping LinkedIn directly breaches its terms, so only a licensed provider is used. Under the DPDP Act, enrichment needs a stated purpose and notice. The gate form shows: "We may use your professional details from public sources to personalise your visit" with a checkbox. No checkbox, no enrichment. Enrichment data is deleted after 12 months if the family does not enrol.

### Visitor dashboard (/admin/visits)

- Live board: columns by status, timers for waiting families (alert if waiting > 10 min with no counsellor).

- Today: expected vs arrived vs no-show, counsellor load.

- Analytics: visits per day/week, peak hours, average wait, session and tour length, visit → application conversion by counsellor and source, no-show rate.

- Logs: searchable list, export CSV (admin only).

## B. Recording the counselling conversation

- The counsellor wears a recorder (device choice and the full metrics are in section 21).

- "Start session" in the CRM links the recording window to the visit. When the device syncs, the audio file is uploaded to the private documents bucket (section 2) and matched to the visit by counsellor + time.

- Pipeline: upload → speech-to-text with speaker labels (Sarvam Saarika for Indian English, Kannada, Hindi and code-mixed speech; AWS Transcribe as fallback) → Claude analysis → stored on the visit:

  - summary, child's needs, parent's concerns (fees, transport, curriculum, safety), objections and how they were handled

  - questions the counsellor could not answer (fed back to content and training)

  - interest score, next best action, suggested follow-up message

  - counsellor quality scores (talk ratio, discovery questions asked, key points covered) for section 21

- Consent: a visible notice at reception and a spoken line at the start ("This conversation is recorded to help us serve you better"). A parent who says no gets an unrecorded session; the counsellor taps "No recording". Audio is kept 180 days, transcripts 1 year, unless the family enrols and agrees otherwise.

## C. Follow-up and post-visit communication

After left_campus, the CRM starts a follow-up plan driven by the AI summary:

| When | Channel | Content |
| --- | --- | --- |
| +1 hour | WhatsApp | Thank you, brochure PDF, walkthrough video, the counsellor's contact, answers to questions raised in the session |
| +1 day | Email (Gmail-quality template from SES; or Gmail API from the counsellor's mailbox if Google Workspace is used) | Personal summary, fee sheet for the grade, next steps |
| +3 days | AI voice call (Sarvam agent, section 22) | "Do you have any questions? Shall we book the child interaction?" with handover to the counsellor |
| +7 days | SMS | Reminder of admission timeline / seats |
| Ongoing | WhatsApp broadcasts | Events, open days, achievements (brand recall), only with opt-in |
| Enrolled | WhatsApp + email | Welcome, onboarding, then upsell: transport, after-school programmes, sports academy, aptitude tests (section 20) |

Rules: stop the sequence when the stage changes (enrolled, lost), respect quiet hours (no calls before 09:00 or after 21:00), honour opt-out on every channel, and log every message on the lead timeline.

## Data model

| Collection | Key fields |
| --- | --- |
| visits | lead, campus, purpose, slot, status, history[], pass code, gate, counsellor, guide, recording, transcript, aiSummary, scores |
| visitors | phone (verified), name, blacklisted, consent flags (enrichment, recording, marketing) |
| enrichments | visitor, provider, raw payload, fetchedAt, expiresAt |
| followUps | lead, step, channel, scheduledAt, sentAt, status, content |

## Build order

- 30 Nov – 18 Dec: visits collection, statuses, gate page with OTP, live board (no enrichment).

- 4 – 15 Jan: alerts, analytics, guard view, kiosk mode.

- 11 – 22 Jan: Apollo enrichment job + profile card, consent texts.

- 18 Jan: pilot at Nagarbhavi with the real front desk.

- 18 Jan – 29 Jan: recording link and follow-up sequences (depends on sections 21 and 22 for devices and voice).

## Acceptance

- A parent can go from gate QR to digital pass in under 60 seconds.

- The counsellor receives an alert within 10 seconds of OTP success.

- Every admission visit has a status history and ends in left_campus or no_show.

- No enrichment or recording without a stored consent flag.

## Open questions

- How many entrances does the Nagarbhavi campus have, and is there a guard post with a phone or tablet?

- Does ULL use Google Workspace (Gmail API follow-ups from the counsellor's own mailbox) or Microsoft 365?

- Apollo plan and credits budget per month?

# 7. Website with CMS, AI content intake and SEO validation

The content team drafts in Claude or ChatGPT and pastes the result into the CMS, which turns it into page-builder blocks they can then edit visually. Every page passes SEO and quality checks before it can be published. Builds on the existing Payload CMS at /admin and the Puck page builder at /editor. 2 Nov – 11 Dec 2026.

### Key actions

- Publish a content schema (JSON) and a prompt pack so Claude/ChatGPT output maps 1:1 to our blocks

- Add "Import from AI" in /admin that accepts Markdown or JSON, validates it and creates a draft page

- Add in-CMS AI actions (write meta description, suggest alt text, shorten, translate, FAQ from page) behind a provider adapter (Claude default, OpenAI optional)

- Add SEO fields (meta title, canonical, noindex, OG image, focus keyword, schema type) to Pages

- Block publishing when SEO or quality checks fail; show a score panel in the editor sidebar

- Add a Redirects collection that feeds the CloudFront function and the sitemap

- Add News, Events, Faculty and FAQs collections with their own JSON-LD

- Add the cookie consent banner and GA4/Meta pixel loading after consent

## What exists

- Payload CMS at /admin with Pages (title, slug, description ≤ 170, hero, breadcrumb, blocks), Media, SiteSettings.

- Blocks: text, cards, table, steps, faq, quote, gallery, cta, subnav, enquiry (cms/src/blocks/index.ts).

- Puck visual page builder at /editor/ with phone/tablet/desktop preview, drafts and publish; Live Preview in Payload. Publishing triggers the static rebuild (cms/src/lib/rebuild.ts).

- web/src/app/sitemap.ts and robots.ts.

## 1. AI content intake

### The flow

### Two input formats

- Markdown (easiest for writers). Rules in the prompt pack: one # title, ## per section, a front-matter block for slug, metaTitle, description, brand. The importer maps patterns to blocks: a ## section with prose → text; a list of ### Title + paragraph → cards; Q:/A: pairs → faq; numbered steps → steps; a > quote → quote; a two-column table → table; a final "Book a visit" section → cta.

- JSON (exact). We publish cms/content-schema.json, generated from the block configs, so Claude or ChatGPT (structured output / JSON mode) returns a valid blocks array directly.

### Prompt pack (stored in the CMS as a global, so the content lead can tune it)

- Brand voice: warm, clear, parent-first, no superlatives without proof ("best school" is banned unless an award is cited), Indian English spelling.

- Facts sheet per brand (grades, board, address, programmes) so the AI doesn't invent facts.

- Output rules: block types allowed, word limits per block, meta title 50–60 chars, description 140–160 chars.

- A "do not claim" list: fees, results, rankings, IB authorisation wording (section 5).

### In-CMS AI actions

Buttons on fields and blocks, calling Claude through a server route (/api/ai/*, staff only, logged):

| Action | Where |
| --- | --- |
| Write meta title / description from page content | SEO tab |
| Suggest alt text from the image (vision) | Media upload |
| Generate FAQ block from the page | Blocks |
| Shorten / simplify / make friendlier | Any text field |
| Translate to Kannada / Hindi (for future language versions) | Page |
| Check facts against the brand facts sheet | Before publish |

Provider adapter: cms/src/lib/ai.ts with anthropic default (claude-sonnet-5-5 for drafting, claude-haiku-5-5 for quick field actions) and an openai option, chosen by env var. API keys live in Secrets Manager. Every call is stored in an aiLogs collection (user, action, tokens) for cost tracking.

## 2. SEO settings per page

Add an SEO tab to Pages (and to News, Events):

| Field | Rule |
| --- | --- |
| Meta title | Required, 30–60 chars, unique across the site, falls back to title |
| Meta description | Required, 120–160 chars (today: max 170), unique |
| Slug | lowercase, a-z0-9-/, no trailing slash, unique, no stop-word bloat |
| Canonical URL | Defaults to self; override for duplicates |
| Robots | index/noindex, follow/nofollow (noindex forced on thank-you, portal, preview) |
| OG image | Required 1200×630; falls back to the hero image |
| Focus keyword | Optional; checked for presence in title, H1, first paragraph and slug |
| Schema type | WebPage, AboutPage, ContactPage, FAQPage, Article, Event, School, Course |
| Breadcrumb | Already exists; drives BreadcrumbList JSON-LD |
| Hreflang | For future Kannada/Hindi versions |

## 3. Validations (block publish on errors, warn otherwise)

| Check | Level |
| --- | --- |
| Meta title and description present, lengths in range, unique | Error |
| Exactly one H1 (the hero heading); headings not skipping levels | Error |
| Every image has alt text (5–125 chars, not the filename) | Error |
| Images ≤ 400 KB after processing; hero ≤ 250 KB; WebP/AVIF sizes generated | Error |
| Internal links resolve to a published page or redirect | Error |
| No external link without rel="noopener"; nofollow on sponsored | Auto-fix |
| Page has at least 300 words (except utility pages) | Warning |
| Focus keyword present where set | Warning |
| Readability (sentence length, passive voice) | Warning |
| Banned claims from the prompt pack ("No.1", "best" without source) | Error |
| Phone/address match the campus record (NAP consistency) | Error |
| Enquiry/visit CTA present on brand and campus pages | Warning |
| Fact check against brand facts sheet (AI, optional) | Warning |

A sidebar panel in both /admin and the page builder shows a score (0–100), the list of failed checks, and "Fix with AI" where possible. Validation runs in a Payload beforeChange hook when _status goes to published, so it cannot be bypassed.

## 4. Site-wide SEO

- Redirects collection (from, to, 301/302) → compiled into the CloudFront function at build time; also used for the /academics/... → /auremont/academics/... move (section 5).

- Sitemap per brand (/sitemap.xml index → /auremont/sitemap.xml, /global/sitemap.xml), rebuilt on publish; ping Search Console.

- JSON-LD: Organization (ULL India) with subOrganization brands, School per campus with address, geo, phone, sameAs socials; FAQPage, Event, NewsArticle, BreadcrumbList, Person (principal, faculty).

- Core Web Vitals budget enforced in CI with Lighthouse CI on 5 key pages: LCP < 2.5s, CLS < 0.1, INP < 200ms, performance ≥ 90.

- Custom 404 with search and CTAs; noindex on preview and editor.

## 5. New content types

| Collection | Why |
| --- | --- |
| news | Fresh, rankable pages; feeds Google Business Profile posts (section 12) |
| events | Open days, workshops; Event schema; registration form → CRM |
| faculty | Teacher profiles build trust (competitors show achievers, not teachers) |
| faqs | Shared FAQ library reused across pages; FAQPage schema |
| downloads | Brochures, fee sheets, prospectus (gated by a short form → CRM lead) |
| testimonials | Parent and student quotes, video links |

## 6. Workflow and roles

- Draft → In review → Published, using Payload versions/drafts. Content editors draft; School admin or Group admin approves.

- Scheduled publish (Payload schedulePublish) for campaign pages.

- Audit trail: who changed what, from versions.

## 7. Cookie consent

Banner with Accept / Reject / Settings (section 3 privacy). GA4, Google Ads and Meta Pixel load only after consent (Google Consent Mode v2). Default: reject non-essential.

## Acceptance

- A writer pastes an AI draft and gets an editable draft page in under a minute, with no developer.

- A page with a missing alt text or a 200-character description cannot be published.

- Lighthouse CI passes on the key pages.

- /admin shows the AI usage cost per month.

## Open questions

- Will writers use Claude, ChatGPT, or both? (Both are supported; the prompt pack is the same.)

- Who approves content (one approver per brand)?

- Are Kannada pages wanted for 2027-28?

# 8. In-house CRM for group admins, school admins and counsellors

Grow the existing Admissions & Visitor Desk (Enquiries collection in Payload) into a full admissions CRM at /admin, with families, children, leads, activities, tasks, a pipeline board, assignment rules, SLAs and reports, scoped by brand and campus. Our database is the system of record. 9 Nov – 18 Dec 2026 for v1.

### Key actions

- Add Families, Children, Leads (replacing Enquiries), Activities, Tasks and Campaigns collections with migrations from Enquiries

- Row-level access by campus for School admin, counsellor and front desk

- Kanban pipeline view, lead detail timeline and quick actions (call, WhatsApp, email, book visit)

- Round-robin and rule-based assignment, first-response SLA with escalation

- Merge duplicates by verified phone and email

- Role dashboards for Group admin, School admin and counsellor

- CSV import for walk-in registers and past spreadsheets; CSV export for admins

## Users and what they see

| Role (from cms/src/access/roles.ts) | Scope | Main screens |
| --- | --- | --- |
| Group admin (admin) | All brands and campuses | Group dashboard, all pipelines, reports, users, settings, integrations |
| School admin (schoolAdmin) | Their campuses | Campus dashboard, pipeline, counsellor performance, approvals, content |
| Admissions counsellor (counsellor) | Leads assigned to them (and unassigned in their campus) | My day, my pipeline, tasks, calls, visits |
| Front desk (frontDesk) | Their campus visits | Visitor board (section 6), walk-in entry |
| New: Marketing (marketing) | Read-only leads, full campaigns | Source and campaign reports (section 18) |
| New: Tele-caller (telecaller) | Assigned call lists | Call queue, dispositions |

## Data model

| Collection | Key fields |
| --- | --- |
| families | primary contact (name, verified phone, email), secondary contact, address, pincode, language, consent flags, external CRM ids (section 19) |
| children | family, name, DOB, gender, current school, current grade, sibling flag |
| leads | family, child, brand, campus, academic year, grade sought, stage, owner, score, source + attribution (section 18), lost reason, expected join date, fee band, tags |
| activities | lead, type (call, WhatsApp, email, SMS, visit, note, stage change, AI call, form), direction, summary, recording link, by, at |
| tasks | lead, type, due at, owner, status, created by rule or user |
| campaigns | name, channel, budget, dates, brand, UTM campaign |

enquiries is migrated into families + children + leads (one-time migration script; the website form keeps posting to /api/enquiries, which becomes a thin endpoint creating a lead).

### Pipeline stages (from STAGES today, per campus configurable)

New → Contacted → Visit booked → Visited → Child interaction → Documents pending → Offer made → Admission confirmed (fee paid) → Enrolled, plus Lost with a required reason (fees, distance, curriculum, chose competitor (which), no response, not eligible, next year).

## Screens

- Counsellor "My day": today's visits, overdue tasks, new leads to call, callbacks due; one-tap call (click-to-call via the telephony provider, section 22) and WhatsApp (WATI).

- Pipeline board: Kanban by stage with drag-and-drop, filters (campus, grade, source, owner, year, score), counts and values per column.

- Lead detail: family and child card, timeline of every activity, AI summary of the latest conversation (section 21), next best action, tasks, documents, external CRM sync status.

- Lists: saved views ("Grade 1 leads not contacted in 48h").

- Dashboards: see below.

Built as custom Payload admin views (React components registered in payload.config.ts), so they live under /admin with the same login and roles. Heavy lists use the Payload REST/local API with indexes on stage, owner, campus, createdAt.

## Rules and automation

| Rule | Default |
| --- | --- |
| Assignment | Round-robin among counsellors of the campus; by grade band if configured; Meta/Google leads to tele-callers first |
| First response SLA | Call within 15 minutes in working hours (09:00–19:00), else by 10:00 next day; escalate to School admin at 2× SLA |
| Follow-up cadence | Auto tasks after each stage change (e.g. Visited → call in 24h) |
| Duplicate handling | Same verified phone = same family; new lead for the same child + year merges into the open lead and logs the new source as a touch |
| Lead scoring | Grade fit, distance, engagement (pages, opens, replies), visit done, AI interest score; 0–100 |
| Stale leads | No activity 14 days → reminder; 45 days → move to Lost (no response) with confirmation |

## Dashboards

- Group admin: leads, visits, applications, admissions by brand/campus/week; source ROI (section 18 + ad spend); funnel conversion; counsellor league table; seats filled vs target per grade.

- School admin: same for their campus + SLA breaches + today's visits.

- Counsellor: my funnel, my conversion vs campus average, calls made, response time.

## Reports and exports

Funnel by source/grade, time-in-stage, lost reasons, visit to admission, counsellor productivity. CSV export for Group/School admins only, logged.

## Security and privacy

- Row-level access by campus and owner in Payload access functions (not just hidden UI).

- Phone numbers masked for tele-callers except when calling through the system (optional).

- Audit log of views and exports of family records.

- Data retention: lost leads anonymised after 24 months.

## Build order

| Week | Deliverable |
| --- | --- |
| 9 Nov | Data model, migration from Enquiries, campus scoping |
| 16 Nov | Lead detail + timeline, tasks |
| 23 Nov | Pipeline board, assignment, SLA |
| 30 Nov | Dashboards, dedupe, CSV import/export |
| 7 Dec | Hardening, staff training, UAT with counsellors |
| 14 Dec | Live with the website |

## Acceptance

- Every website, ad and walk-in lead appears in the CRM within 1 minute with an owner.

- A counsellor sees only their campus.

- SLA breach alerts fire.

- The Group admin dashboard shows the full funnel by source for the season.

## Open questions

- How many counsellors and tele-callers at launch?

- Are seat targets per grade available for 2027-28?

- Is there an existing spreadsheet of leads to import?

# 9. SSO for admins (Microsoft Entra ID) and for parents and students

Staff sign in to /admin with their Microsoft work account through Entra ID (OIDC), with Entra groups mapped to CRM roles. Parents and students sign in to their dashboards with phone OTP, plus Google sign-in, and the same identity is handed to ullindia.aptitudetest.in. Staff 2 – 20 Nov 2026; families 4 – 29 Jan 2027.

### Key actions

- Tenant admin registers an Entra ID app (redirect URIs for uat and prod) and creates security groups per role and campus

- Add an OIDC auth strategy to the Payload Users collection; map group claims to roles and campuses on each login

- Keep one local break-glass admin account with a long password and MFA, stored in a vault

- Add a portalUsers auth collection for parents and students with phone OTP and Google sign-in

- Decide student login rules by age (parent-managed under 13, own login 13+)

- Implement the identity handoff to ullindia.aptitudetest.in per their integration docs (section 20)

The user wrote "Intra ID"; this is Microsoft Entra ID (formerly Azure AD).

## A. Staff: Microsoft Entra ID → /admin

### Flow

### Setup (tenant admin, one-time)

- App registration "ULL CMS", single-tenant.

- Redirect URIs: https://uat.ullindia.com/api/auth/entra/callback, https://ullindia.com/api/auth/entra/callback, http://localhost:3000/api/auth/entra/callback.

- Token configuration: add groups claim (security groups), or app roles (cleaner: roles appear as roles claim).

- Groups (or app roles):

| Entra group / app role | Payload role | Campus |
| --- | --- | --- |
| ULL-CMS-GroupAdmin | admin | all |
| ULL-CMS-SchoolAdmin-Nagarbhavi | schoolAdmin | nagarbhavi |
| ULL-CMS-Editor | editor | all |
| ULL-CMS-Counsellor-Nagarbhavi | counsellor | nagarbhavi |
| ULL-CMS-FrontDesk-Nagarbhavi | frontDesk | nagarbhavi |
| ULL-CMS-Marketing | marketing | all |

- Conditional Access: require MFA for this app (recommended).

### Code

- cms/src/lib/auth/entra.ts: OIDC client (openid-client), PKCE, state + nonce checks, token verification against Entra's JWKS.

- Users collection: auth: { strategies: [entraStrategy], disableLocalStrategy: false } during migration; set disableLocalStrategy: true later except for the break-glass account.

- Roles and campuses are overwritten from Entra on every login, so removing someone from a group removes access at next login. A nightly job (Microsoft Graph, GroupMember.Read.All) deactivates users who were removed or disabled, so access ends even if they never log in again.

- Secrets (ENTRA_TENANT_ID, ENTRA_CLIENT_ID, ENTRA_CLIENT_SECRET) in Secrets Manager.

- Login page: Payload's admin login gets a "Sign in with Microsoft" button (custom beforeLogin component).

### If staff use Google Workspace instead

Same OIDC strategy with Google as issuer; groups via Cloud Identity. Decide once the domain email setup is known (section 2).

## B. Parents and students → dashboards

### Recommendation

A separate Payload auth collection portalUsers, so families never share a table or cookie with staff.

| Method | Who | Notes |
| --- | --- | --- |
| Phone OTP (primary) | Parents | Same OTP service as the visitor gate (section 6): WhatsApp first, SMS fallback. Phone is already the key in the CRM, so a parent who enquired is recognised at first login |
| Google sign-in | Parents, students 13+ with school Google accounts | OIDC; email must match a family contact or be invited |
| Microsoft sign-in | Students, if the school issues Microsoft 365 student accounts | Same Entra tenant, a different app/group |
| Email magic link | Fallback | For NRI parents without an Indian number |

### Family identity model

- portalUsers: id, type (parent, student), phone (verified), email, linked family, linked child (for students), consent records.

- A parent sees all children in their family (section 11). A second parent is invited by the first, or added by the school.

- Students: under 13 the dashboard is opened through the parent's login ("Switch to Aarav's view"); 13+ get their own login, invited by the parent or the school. DPDP rules on children's data need verifiable parental consent, which the parent gives when activating the student account.

- Sessions: 30 days for parents on trusted devices, 12 hours for students; refresh on activity.

### Hand-off to ullindia.aptitudetest.in (section 20)

When a student or parent clicks "Take test" or "View report", we send them to aptitudetest.in already signed in. Options, decided by their integration docs:

- OIDC: ULL acts as an identity provider (Payload issues ID tokens; needs a small OIDC provider such as oidc-provider).

- Signed JWT launch link (likely simplest): https://ullindia.aptitudetest.in/sso?token=<JWT> signed with a shared secret or our private key, 2-minute expiry, containing ULL student id, name, grade, parent email/phone.

- SAML: only if they require it.

## Security checklist

- PKCE + state + nonce on every OIDC flow.

- Cookies: HttpOnly, Secure, SameSite=Lax, scoped to ullindia.com.

- OTP: 6 digits, 5-minute expiry, 3 attempts, rate limit per phone and IP (WAF, section 2).

- Login audit log (who, when, IP, method) for staff and families.

- Break-glass admin: one local account, password in a vault, alert when used.

## Acceptance

- A counsellor added to the Nagarbhavi counsellor group in Entra can sign in and sees only Nagarbhavi leads; removed from the group, they lose access within 24 hours.

- A parent who enquired with their phone signs in with OTP and sees their child.

- A student is sent to aptitudetest.in without a second login.

## Open questions

- Is ULL on Microsoft 365 (Entra ID tenant exists) and who is the tenant admin?

- Do students get school email accounts (Google or Microsoft)?

- Will aptitudetest.in accept OIDC, a signed JWT, or SAML?

# 10. Student dashboard

A student-facing dashboard showing the academic calendar, current grade, subjects and curriculum, progress reports, and a portfolio of everything the student does (learning, quizzes, Q&A, sports, participation, psychometric tests). Metrics follow CBSE/NEP 2020's Holistic Progress Card for Auremont and IB learner profile and criteria for Global. 1 Feb – 9 Apr 2027, beta for one grade band.

### Key actions

- Identify the school ERP/LMS (attendance, marks, timetable) and agree an import or API

- Academic heads sign off the metric framework below for CBSE and IB

- Add academic years, terms, grades, sections, subjects, curriculum units, assessments, results, attendance, activities and achievements collections

- Build the dashboard (home, calendar, subjects, progress, portfolio, tests) under /portal/student

- Give teachers a quick-entry screen for observations, participation and competency ratings

- Parental consent and age-appropriate design (no ads, no tracking, no public profiles)

URL: ullindia.com/portal/student (login from section 9). Under 13, the parent opens it in "student view" (section 11).

## Screens

| Screen | Content |
| --- | --- |
| Home | Greeting, today's timetable, homework due, next test, latest teacher note, streak/badges, upcoming events |
| Academic calendar | Term dates, holidays, exams, PTMs, events, sports days; per grade/section; .ics subscribe link |
| My grade | Current grade and section, class teacher, subjects and teachers, timetable |
| Subjects | Per subject: curriculum units for the year (from the CBSE syllabus / IB unit planner), unit status (upcoming, in progress, done), resources, quizzes, Q&A, marks |
| Progress | Term reports, competency progress, trend charts, teacher comments, Holistic Progress Card view |
| Portfolio (digital footprint) | Projects, artwork, robotics builds, presentations, certificates, sports results, clubs, competitions, reflections; photos and files |
| Tests and reports | Psychometric tests from ullindia.aptitudetest.in with status and report PDFs (section 20) |
| Wellbeing | Mood check-in (optional, 13+), counsellor booking, Kushala programme |

## Metric framework (suggested)

### 1. Academic

| Metric | Source | Shown as |
| --- | --- | --- |
| Attendance % (term, year) | ERP | Number + trend |
| Assessment scores per subject (periodic tests, half-yearly, annual) | ERP / teacher | Score, class average band (not rank) |
| Competency mastery per learning outcome | Teacher ratings, quizzes | Beginner / Proficient / Advanced per outcome |
| Homework completion rate and on-time rate | LMS / teacher | % |
| Quiz accuracy and attempts | In-app quizzes | % + improvement |
| Questions asked / answered (Q&A) | In-app Q&A | Count, quality badge |
| Reading log (books, minutes) | Student / parent | Count |
| Curriculum coverage | Unit status | % of year done |

### 2. Holistic (CBSE / NEP 2020 Holistic Progress Card, PARAKH)

HPC asks for self, peer and teacher assessment across domains. Track:

- Physical development, socio-emotional skills, cognitive development, language and literacy, aesthetic and cultural development, positive learning habits.

- Self-assessment and peer feedback each term (simple rubrics with emojis for the Foundational stage).

### 3. IB (ULL Global)

- PYP: learner profile attributes (inquirer, thinker, communicator, risk-taker, knowledgeable, principled, open-minded, caring, balanced, reflective), units of inquiry, exhibition.

- MYP: criteria A–D per subject group (1–8), Approaches to Learning skills (thinking, communication, social, self-management, research), service as action, personal project.

### 4. Sports and fitness

- Fitness test results (Khelo India fitness protocol by age: BMI, flexibility, speed, endurance, strength).

- Sports chosen, coaching sessions attended, matches, medals, house points.

### 5. Participation and co-curricular

- Clubs (Pulse, Ruchi, Aurora Lab, Summit Pathway), events, competitions, Olympiads, MUN, performances, leadership roles, service hours.

### 6. Future readiness

- Psychometric results summary (interest, aptitude, learning style; section 20).

- Stream selector and career test recommendations (Grades 8–10).

Rules: show growth against the student's own past, not class rank. No public leaderboards. Badges for effort and consistency, not only scores.

## Data sources

| Data | Where it comes from |
| --- | --- |
| Timetable, attendance, marks, fees | The school ERP. Unknown today: common ones in India are Entab, Fedena, Teachmint, MyClassboard, Edunext. We import nightly (API or CSV drop to S3) |
| Curriculum units | Academic team in CMS (one-time per year per grade) |
| Quizzes, Q&A | Built in this portal (simple MCQ + short answer), or from the LMS if there is one |
| Observations, participation, competency ratings | Teacher quick-entry screen (mobile-friendly, 30 seconds per entry) |
| Sports | Coaches enter results |
| Psychometric | aptitudetest.in webhook + API (section 20) |
| Portfolio | Student / teacher uploads to the private documents bucket (section 2) |

## Data model (new collections)

academicYears, terms, grades, sections, subjects, curriculumUnits, enrolments (student ↔ section ↔ year), assessments, results, attendance, competencyRatings, activities, achievements, portfolioItems, quizzes, quizAttempts, questions. Students are children from the CRM (section 8) with an enrolled status, so the admissions record carries into school life.

## Teacher input

- Mobile web screen: pick section → student(s) → type (observation, participation, competency, achievement) → rubric → optional photo.

- Bulk entry for a whole class after an event.

- AI help: turn a teacher's short note into a parent-friendly comment (Claude), teacher approves.

## Privacy and safety

- Verifiable parental consent before a student account is active (section 9).

- No third-party trackers or ads on /portal/*.

- Students see only their own data; no messaging between students.

- Files served with presigned URLs only.

## Build order

- Feb: data model, ERP import, calendar, grade and subjects screens.

- Mar: progress, portfolio, teacher entry, aptitude test tiles.

- 9 Apr: beta for one grade band (for example Grades 6–8), feedback, then roll out at the start of 2027-28.

## Acceptance

- A student sees their timetable, calendar, subjects and the latest results without asking a teacher.

- Teachers can log an observation in under 30 seconds.

- Each metric in the framework has a defined source and an owner.

## Open questions

- Which ERP/LMS does ULL Auremont use, and does it have an API?

- Does the academic team want HPC-style reports generated from this system?

- Are students given devices or school accounts?

# 11. Parent dashboard

Parents see the same student metrics as section 10, in a parent view, for one or several children, plus a weekly progress report and a forward roadmap sent every week. Also covers admissions status for prospective families, fees, PTMs and messages. 15 Feb – 23 Apr 2027.

### Key actions

- Child switcher across siblings, including children in different ULL schools

- Generate a weekly report per child (Sunday evening) with an AI-written summary and roadmap, reviewed by rules before sending

- Deliver the weekly report on WhatsApp (summary + link), email and in the dashboard

- Show admission status, documents and visit booking for families who have not enrolled yet

- Fees due and pay (section 3), PTM booking, leave requests, messages to class teacher

- Parent controls for student account, consent, notifications and data download

URL: ullindia.com/portal (phone OTP login, section 9). One login per parent; both parents can have their own.

## Two modes, one portal

| Family state | What they see |
| --- | --- |
| Prospective (lead in CRM) | Application status by child (stage from section 8), documents to upload, visit booking and pass (section 6), messages, psychometric test invites (section 20), brochure and fee sheet |
| Enrolled | Everything below |

## Enrolled parent: screens

| Screen | Content |
| --- | --- |
| Home | Child switcher; this week at a glance per child: attendance, homework done, new results, teacher notes, upcoming events, fees due |
| Progress | The same metrics as the student dashboard (section 10) in parent language: competency progress, scores vs the child's own trend, Holistic Progress Card, sports and participation |
| Weekly report | Archive of weekly reports, each with summary and roadmap |
| Roadmap | What's coming: units next 2–4 weeks, tests, events, and what the parent can do at home |
| Calendar | School calendar merged for all children; .ics subscribe |
| Tests and reports | Psychometric status and reports (section 20) |
| Fees | Dues, receipts (with entity details, section 3), pay online |
| PTM and meetings | Book PTM slots, counsellor sessions |
| Messages | Class teacher and office (moderated, school hours) |
| Settings | Notifications per channel, student login (13+), consents, download my data |

## Weekly progress report

### Content (per child)

- This week in one paragraph (AI-written from the data, warm and specific).

- Highlights: best moments (achievement, good quiz, teacher praise).

- Numbers: attendance, homework on time, quizzes taken and accuracy, reading minutes; arrows vs last week.

- Learning: units covered by subject, competencies that moved up.

- Watch: gentle flags (missed homework twice, a dip in one subject), never more than two.

- Roadmap for next week: units starting, tests, events, what to bring.

- Try at home: one or two activities linked to the units.

- Teacher's note (optional, if the teacher added one).

### Generation pipeline

- Runs Sunday 17:00 IST as a job (SQS worker, section 2).

- The LLM only receives the facts JSON and must return structured output; numbers in the text are checked against the facts. If a check fails, a template version is sent instead.

- Class teachers can preview and add a note until Sunday 12:00 (optional).

- Model: claude-sonnet-5-5; about 1–2k tokens per child per week.

### Multiple children

One message per parent per week with a section per child (not one message per child), so siblings don't flood the parent.

## Notifications

| Event | Channel |
| --- | --- |
| Weekly report | WhatsApp template + email |
| Absent today | WhatsApp/SMS same morning |
| New result published | Push/WhatsApp |
| Fee due in 7 days / overdue | WhatsApp, then AI voice call (section 22) |
| PTM slots open | WhatsApp |
| Event reminder | WhatsApp |

Push notifications: web push now (PWA, "Add to home screen"); a native app later only if usage justifies it (competitors use third-party parent apps such as MyClassboard/Hubblehox; a branded PWA avoids that cost).

## Privacy

- Parents see only children linked to their family; adding a family member requires school verification.

- Divorce/custody flags: the school can restrict one parent's access.

- Data download (DPDP right of access) as a ZIP of reports.

## Acceptance

- A parent with two children gets one weekly WhatsApp with both, opens the link and lands in the report.

- Every number in the AI text matches the dashboard.

- Prospective families can track application status without calling the school.

## Open questions

- Weekly report send time (Sunday evening proposed)?

- Should teachers approve each report, or only add optional notes?

- Languages for the report (English only, or Kannada/Hindi too)?

# 12. Google Business Profile connector in the admin portal

Connect each campus's Google Business Profile to /admin so admins can keep name, address, phone and hours in sync from the CMS, publish posts from News and Events, read and reply to reviews with AI-suggested replies, upload photos, and see profile insights. 4 – 22 Jan 2027; apply for API access in week 1.

### Key actions

- Apply for Google Business Profile API access in Google Cloud (approval can take weeks)

- Verify the ULL Auremont School, Nagarbhavi profile and add the ULL Google account as owner

- Build the OAuth connection (business.manage scope) with refresh tokens in Secrets Manager

- Sync NAP, hours, website, description and attributes from the Campuses collection

- Reviews inbox with AI-suggested replies, approval and SLA

- Publish posts from News/Events and upload photos from the media library

- Pull performance metrics daily into the dashboards (sections 14 and 17)

## Why

For "CBSE school near me" and "school in Nagarbhavi", the Google Maps result appears above the website. Reviews, photos, posts and accurate hours drive calls and visits. Competitors list many campuses but none of the sites studied link reviews or show GBP data (section 15).

## Before any code

- Create or claim the profile "ULL Auremont School" at the Nagarbhavi address; category "CBSE school" (primary), "School", "Private school" (secondary). Verify by video or postcard.

- Owner: a ULL Google account (not a personal one); managers: marketing lead.

- Google Cloud project "ull-gbp" → request Business Profile API access via Google's request form. Without approval the quota is 0.

- Enable: My Business Account Management, Business Information, Business Profile Performance, and the v4 endpoints for reviews, local posts and media.

## Architecture

- OAuth 2.0 with scope https://www.googleapis.com/auth/business.manage, connected once by the Group admin ("Connect Google Business Profile" button). The refresh token is stored encrypted in Secrets Manager.

- Each campus record stores its GBP accountId and locationId.

## Features

| Feature | API area | Notes |
| --- | --- | --- |
| Location sync (name, address, phone, website, hours, special hours for holidays, description, attributes) | Business Information API (locations.patch) | Campuses collection is the source of truth; changes push automatically; Google-suggested edits shown for accept/reject |
| Holiday hours | Business Information specialHours | Filled from the academic calendar (section 10) |
| Reviews inbox | v4 accounts.locations.reviews list + updateReply | New review → alert to School admin; Claude drafts a reply in the school's voice; admin edits and approves; target reply within 24h; never auto-post replies to negative reviews |
| Review requests | – | After enrolment or a good visit, a WhatsApp message with the review link (g.page/r/...), sent by the CRM (section 8). Never offer incentives for reviews (Google policy) |
| Posts | v4 localPosts | "Publish to Google" toggle on News and Events; types: update, event (with dates), offer (open day); image from the CDN |
| Photos | v4 media | Push selected gallery albums (campus, classrooms, sports) |
| Insights | Business Profile Performance API (fetchMultiDailyMetricsTimeSeries) | Calls, direction requests, website clicks, impressions (Search/Maps, mobile/desktop), search keywords monthly |
| Q&A | – | Google has retired the Q&A API; handle FAQs on the website and in posts instead |

## Admin screens

- Overview: rating, review count, new reviews, reply time, last 28 days of calls/directions/website clicks vs previous period.

- Reviews: list with filters (rating, replied/unreplied), AI draft, approve.

- Posts: scheduled and published posts, quick create.

- Profile: diff between CMS and Google, sync status, last push.

## Data model

gbpLocations (campus, ids, last sync), gbpReviews (reviewId, rating, text, reviewer, createdAt, reply, repliedBy, status), gbpPosts (source doc, type, status, Google name), gbpInsights (date, metric, value).

## Metrics (feed section 17)

Average rating, review count growth, reply rate and median reply time, calls, direction requests, website clicks from GBP, top search keywords.

## Acceptance

- Changing campus hours in the CMS updates Google within an hour.

- A new review shows in /admin within a day with an AI draft reply.

- A News item can be posted to Google with one toggle.

- Insights appear on the Group admin dashboard.

## Open questions

- Does a GBP listing already exist for the campus, and who owns it?

- Who approves review replies (School admin or marketing)?

# 13. CDN for all media uploads and references

Every upload and every media reference is stored in that stage's S3 bucket and served from its CloudFront CDN (cdn.ullindia.com / cdn-uat.ullindia.com) under content-hashed, immutable URLs. Private files (documents, recordings, reports) go to a separate private bucket with signed URLs. Most of this is already built and awaiting release. 26 Oct – 6 Nov 2026.

### Key actions

- Commit storage.ts, media-prefix.ts, the two media migrations, publish-assets.mjs and cdn-assets.json, with the media-prefix test

- Backfill existing local uploads to S3 under hashed prefixes and rewrite stored URLs

- Make every media reference (blocks, rich text, SEO OG image, News, Faculty) resolve through publicMediaUrl

- Generate AVIF/WebP sizes on upload, enforce size limits, and strip EXIF location data

- Decide video hosting (YouTube embed by default; S3 + CloudFront for short loops)

- Route private uploads (applicant documents, recordings, reports, portfolios) to the private bucket with presigned URLs

- Add a build check that fails if any page references a non-CDN media URL

## Status today

| Piece | File | State |
| --- | --- | --- |
| S3 upload adapter that writes to the stage media bucket and returns CDN URLs | cms/src/lib/storage.ts | built, awaiting release |
| Content-hash prefix media/<8 hex>/ | cms/src/lib/media-prefix.ts + cms/tests/media-prefix.test.ts | built, awaiting release |
| DB migrations for the prefix and object key | cms/src/migrations/20261023_* | built, awaiting release |
| Site assets (web/public/assets) uploaded as assets/<hash>/<name> with a manifest | deploy/publish-assets.mjs, web/src/content/cdn-assets.json | built, awaiting release |
| CDN distribution with 1-year immutable caching | infra/lib/stage-stack.ts | deployed |
| Local dev falls back to disk when S3_BUCKET/CDN_HOST are unset | storage.ts | written |

Design: replacing a photo writes a new hash and a new URL; old objects stay so pages still pointing at them keep working; S3 versioning is on.

## Remaining work

### 1. Commit and roll out

- Commit the files above, run migrations on UAT, upload a test image, and confirm the URL is https://cdn-uat.ullindia.com/media/<hash>/<file> and that the response has Cache-Control: public, max-age=31536000, immutable.

- Promote to prod.

### 2. Backfill

One-time script deploy/backfill-media.mjs: for each media doc whose file is on local disk, hash it, upload all sizes under the prefix, update prefix/object key, and verify with a HEAD request. Dry-run mode first. Then web is rebuilt so pages point at the CDN.

### 3. Every reference goes through one function

All places that render media must call publicMediaUrl() (or read the stored url, which already holds the CDN URL):

- Page hero, text, gallery, cta, cards blocks.

- Rich text (Lexical) upload nodes.

- SEO OG image and JSON-LD image/logo.

- New collections in sections 7, 10, 16 (News, Events, Faculty, Testimonials, Downloads).

- web/src/content/assets.ts for brand files via cdn-assets.json.

Build check: after next build, scan web/out/**/*.html for src=/href= pointing at /media/ or the EC2 origin and fail the deploy if any are found.

### 4. Image pipeline

- On upload (Payload imageSizes + sharp): thumb 400, card 800, hero 1600, og 1200×630, each as WebP and AVIF; original kept.

- Limits: images ≤ 10 MB upload, auto-compressed; reject < 800 px wide for hero use.

- Strip EXIF (especially GPS) for privacy, keep orientation.

- <picture> with AVIF → WebP → JPEG fallback and width/height to avoid layout shift.

- Alt text required (section 7).

### 5. Documents and downloads (public)

Brochures and fee sheets (PDF) go to the media bucket under docs/<hash>/<name>.pdf and are served from the CDN. If they are gated behind a form (section 7 downloads), the page shows the form first and then reveals the CDN link; the link is not secret, which is acceptable for brochures.

### 6. Video

| Type | Where |
| --- | --- |
| Walkthrough, brand film, stories, aftermovies | YouTube (free hosting, reach, SEO); embed with a lightweight facade (thumbnail first, player on click) to protect LCP |
| Short silent loops (hero background, 5–10 s) | MP4/WebM in the media bucket via CDN, ≤ 3 MB, preload="none" on mobile |

### 7. Private files (never on the public CDN)

| File | Bucket | Access |
| --- | --- | --- |
| Applicant documents (birth certificate, TC, report cards) | Private documents bucket (section 2) | Presigned GET, 5 min, after a role check |
| Counselling recordings and transcripts (sections 6, 21) | Private | Counsellor, School admin |
| Psychometric reports (section 20) | Private | Family + counsellor |
| Student portfolio uploads (section 10) | Private | Student, parents, teachers |

A separate Payload upload collection privateFiles with disablePayloadAccessControl: false, so every download passes access checks.

## Acceptance

- No HTML page in web/out references media outside the CDN host.

- Replacing an image changes its URL, and the old URL still returns 200.

- Images are served as AVIF/WebP with long cache headers.

- Private files return 403 without a valid presigned URL.

# 14. Social media and metrics dashboard for the group admin

One dashboard in /admin where the Group admin sees social media performance (Instagram, Facebook, YouTube, LinkedIn), paid ads (Meta, Google), web analytics (GA4, Search Console) and Google Business Profile next to CRM outcomes, by brand and campaign. Data is pulled daily through the platforms' APIs. 11 Jan – 5 Feb 2027.

### Key actions

- Get API access for Meta (Business Manager system user), YouTube Analytics, LinkedIn Community Management, GA4 Data API, Search Console API and Google Ads API

- Decide to build (recommended) or to use a third-party tool and embed it

- Write daily collectors per platform into a metrics table

- Build the Group admin dashboard with brand and date filters, and a weekly PDF/email

- Join spend and clicks to CRM leads, visits and admissions through UTM campaign (section 18)

## Build or buy

| Option | Pros | Cons |
| --- | --- | --- |
| Build in /admin (recommended) | Joins social and ad data with CRM outcomes (cost per admission), one login, no per-seat fees | API approvals and maintenance |
| Tool (Metricool, Sprout Social, Hootsuite, Zoho Social) | Fast, includes scheduling | Can't see admissions; extra cost; data in another place |

Recommendation: build the reporting, and use a scheduling tool only if the social team wants one (Meta Business Suite is free for FB/IG scheduling).

## Sources and metrics

| Source | API | Daily metrics |
| --- | --- | --- |
| Instagram (per brand) | Instagram Graph API via Meta Business Manager | Followers, reach, impressions, profile visits, website taps, per-post reach, saves, shares, Reel plays, engagement rate |
| Facebook page | Graph API Page Insights | Followers, reach, engagement, video views |
| YouTube channel | YouTube Analytics API + Data API | Subscribers, views, watch time, average view duration, CTR, top videos, traffic sources |
| LinkedIn page | LinkedIn Community Management API (needs app review) | Followers, impressions, clicks, engagement |
| Meta Ads | Marketing API (Insights) | Spend, impressions, reach, CPM, clicks, CTR, leads (Lead Ads), cost per lead, by campaign/ad set/ad |
| Google Ads | Google Ads API (developer token) | Spend, clicks, CPC, conversions, cost per conversion, search terms |
| GA4 | Analytics Data API | Users, sessions, engaged sessions, conversions (enquiry_submitted, visit_booked) by source/medium/campaign, landing pages |
| Search Console | Search Console API | Clicks, impressions, CTR, average position, top queries and pages |
| Google Business Profile | Section 12 | Calls, directions, website clicks, rating |
| CRM | Section 8 / 18 | Leads, visits, applications, admissions by source/campaign |

Access setup: a Meta system user in ULL's Business Manager with a long-lived token; a Google service account added to GA4 and Search Console; OAuth for YouTube, LinkedIn and Google Ads. All tokens in Secrets Manager.

## Storage

One narrow table: metricsDaily(date, source, account, brand, campaign, entity, metric, value) + posts(source, id, brand, publishedAt, type, url, caption) for content performance. Collectors run at 05:00 IST on the SQS worker (section 2) and backfill 30 days on first run.

## Dashboard (/admin/insights)

Filters: date range, brand (Group, Auremont, Global), channel.

- Outcome strip: leads, visits, admissions, cost per lead, cost per visit, cost per admission (spend ÷ admissions with that source).

- Paid: spend vs budget, CPL by campaign, best and worst ads.

- Social: follower growth per platform, reach, engagement rate, top 10 posts by engagement and by leads generated.

- YouTube: views, watch time, top videos, average view duration for the walkthrough.

- Website: sessions by source, conversion rate, top landing pages.

- Search: clicks and impressions trend, top queries, average position for target keywords ("CBSE school Nagarbhavi").

- Local: GBP calls, directions, rating.

- Weekly email to the Group admin every Monday 08:00 with the strip, three wins and three issues (AI-written from the numbers, same guardrails as section 11).

## Acceptance

- Numbers for the last 30 days match each platform's own UI within 5% (platforms restate data for a few days).

- Cost per admission by channel is visible for the season.

- The Monday email arrives with correct numbers.

## Open questions

- Who owns each social account today (personal profiles must move to Business Manager)?

- Is a scheduling tool wanted for the social team?

# 15. Competitor deep study and gap report

A study of Orchids The International School, Ryan Group and VIBGYOR High covering page structure, layout, forms, verification, communication, brochures, offerings, mobile apps and notifications, with a gap report and a must-have feature list for ULL. First pass done from the live homepages on 23 Oct 2026; deeper pass (campus pages, forms end-to-end, apps, mystery-shopping) 26 Oct – 6 Nov.

### Key actions

- Visit 3 campus pages, the admission form, fee page and parent app listing of each competitor; record screenshots in screenshots/competitors

- Submit a test enquiry on each site and log every call, WhatsApp, SMS and email received for 14 days (speed and quality)

- Run Lighthouse and a crawl (titles, meta, schema, sitemap, Core Web Vitals) on each homepage and one campus page

- Add 2–3 local competitors near Nagarbhavi to the study (same grade range, CBSE)

- Review the must-have list with ULL and lock the launch scope for sections 7, 8 and 16

Sources: homepages of orchidsinternationalschool.com, ryangroup.org, vibgyorhigh.com, read on 23 Oct 2026. Items marked "not seen" may be loaded by scripts and need a live check in the deep pass.

## 1. Snapshot

|  | Orchids | Ryan Group | VIBGYOR High |
| --- | --- | --- | --- |
| Scale claimed | 150+ campuses, 20+ cities | 150+ schools, 40+ cities, 8 boards, 50+ years | 41 schools, 15 cities, since 2004 |
| Boards | CBSE, ICSE | CBSE, ICSE, IGCSE, IB | CBSE, CISCE, Cambridge (CIE) |
| Site structure | Paths: /{city}-branches/{campus}, /school-admission-in-{city} | Mixed: paths (/search-result/..., /site/<campus>/), subdomains (ryaninternationalacademy.ryangroup.org), separate domain (ryanglobalschools.com) | Paths: /school/{city}/{board}/{campus}; sister brands on separate domains |
| Main nav | Day & Boarding Schools, Admission, Study Materials, Blogs, Helpdesk, About, More | About, Academics, Admissions, Student Life, Parents Corner, Alumni Connect, Guidance Program | About, Curriculum, Schools, Beyond Academics, Teaching & Learning, Admissions, Locate Us |
| Utility bar | Admissions 2027-28, phone, email, hiring | Phone, "Enquire for Early Bird Benefits", socials | Enquiry Form, Parent Login |
| Enquiry form | Parent, child, mobile (country code), email, city, branch (~130 options), grade | Separate enquiry page; online registration; document list | Academic year, school, first/last name, relation, email, country code, phone, grade, query, math captcha |
| Verification | None seen | Not seen | Math captcha only |
| School locator | City lists + branch dropdown, no map | Board → City → School dropdowns | Map image + locator page |
| Brochure | Not seen | Document list only | Not seen |
| Fees | "Fee Structure" link | Not seen | Not seen |
| Chat / WhatsApp | Not seen | Click-to-call only | Click-to-call only |
| Parent app | Orchids School Connect / Eduvate (footer badges) | Parent portal app (MyClassboard-based) | Parent login on Hubblehox; no app |
| Content hub / SEO play | Very large: NCERT solutions, syllabus, worksheets, calculators, poems | Blog, media, guidance programme | Blog, results |
| Social proof | Toppers, awards, achievers grid | Stats band, award logo wall, roll of honour | Awards carousel, results banners, gallery |
| Alumni | – | Strong: Ryan Connect, notable alumni, diaries | – |
| Virtual tour | Not seen | Video embed | None |
| Title tag | "ORCHIDS The International School ¦ Best CBSE and ICSE Schools in India" | "Top 10 International Schools in India - Ryan Group" (body doesn't deliver a top-10 list) | "Top CBSE, CISCE and CIE Schools in Karnataka, Maharashtra, Gujarat…" |
| Visible issues | Mixed year labels (2026-27 vs 2027-28), unfiltered 130-option branch list | Duplicate menu markup, mismatched app badge alt text, inconsistent /about vs /about-us links, "8 boards" claim with 4 named | Inconsistent footer links (city hub vs single campus), math captcha friction |

## 2. What they do well (copy the idea, not the execution)

- Admissions CTA everywhere with the academic year in the label (all three).

- Find a school by board → city → campus (Ryan) and city landing pages for local SEO (Orchids /school-admission-in-{city}).

- Proof up front: results, toppers, awards, stats band (all).

- Content hub for organic traffic (Orchids' study materials attract parents searching NCERT help).

- Parent life sections: Parents Corner, testimonials, engagement events, refer-a-parent (Ryan).

- Alumni network (Ryan).

- Safety as a selling point on the homepage (VIBGYOR "The VIBGYOR Edge").

- Campus pages with a consistent URL pattern (VIBGYOR).

## 3. Gaps across all three (ULL's opportunity)

| Gap | ULL response | Plan |
| --- | --- | --- |
| No phone verification on enquiry forms → junk leads, slow follow-up | Phone OTP (WhatsApp) on visit booking; light forms stay one step | 06, 08 |
| No instant WhatsApp / chat | WhatsApp click-to-chat with source tagging + AI assistant on the site with human handover | 18, 22 |
| No visible brochure or fee transparency | Downloadable brochure per brand; fee range per grade band on the campus page | 07, 16 |
| No virtual tour | Campus walkthrough video + 360° photos | 04, 16 |
| No visit booking with a slot picker | Book a visit with real slots and a digital pass | 06 |
| Admission status invisible to parents | Applicant view in the parent portal | 11 |
| Parent apps are third-party white labels | Branded PWA portal with weekly reports | 11 |
| Testimonials thin or missing | Parent video stories and quotes per campus | 04, 07 |
| Teachers invisible | Faculty profiles | 07, 16 |
| Mixed domain strategies (Ryan) | One domain with brand paths | 05 |
| Generic SEO titles, missing meta descriptions | Enforced SEO validation per page | 07 |
| No career guidance tools in admissions (only Ryan mentions guidance) | Psychometric tests on ullindia.aptitudetest.in as a lead magnet and student service | 20 |
| Data inconsistency (years, counts) | CMS facts sheet + validation | 07 |

## 4. Must-have features for ULL (launch, 14 Dec)

Page structure

- Group home → brand homes (/auremont, /global) → campus page → admissions.

- Sticky top bar: Admissions 2027-28 · Book a Visit · Enquire · WhatsApp · Parent Login.

- Mega-menu limited to 6 groups (Ryan's 7 deep groups are too much).

Layout (homepage of each brand) Hero with video → proof strip (stats/awards/ambassador) → why us (4 pillars) → academics by stage → sports → beyond the classroom → safety and care → campus tour → parent stories → faculty → news/events → FAQ → visit CTA with map.

Forms

- Enquiry: parent name, phone (+91 default, country code), child name, grade, campus (pre-selected from page), consent. Email optional. Under 30 seconds.

- Visit booking: + date/slot picker, phone OTP, WhatsApp confirmation with pass.

- Brochure download: name + phone, then instant PDF.

- Register interest (ULL Global).

- Hidden fields: UTM, gclid/fbclid, landing page, referrer (section 18).

Verification

- OTP on visit booking and portal login; honeypot + rate limiting on forms (no captcha friction); duplicate detection in CRM.

Communications

- Instant WhatsApp + email acknowledgement; counsellor call within 15 min (section 8 SLA); visit reminders; post-visit sequence (section 6).

Brochures and offerings

- Brand brochure, grade-band fee sheet, transport routes PDF, programme one-pagers (Pulse, Ruchi, Kushala, Aurora Lab, Summit Pathway).

Mobile app and notifications

- PWA portal with web push now; native app only after usage is proven.

After launch (P2)

- City/area landing pages ("CBSE school in Vijayanagar", "school near Rajarajeshwari Nagar"), a parent resources hub (light version of Orchids' study content), alumni/founding families section.

## 5. Deep-pass checklist (26 Oct – 6 Nov)

For each competitor:

- ☐ Homepage, a campus page, admissions page, fee page, contact page: screenshots (desktop + mobile)

- ☐ Full form submission with a test number; record verification, thank-you page, redirects

- ☐ Response log for 14 days: first call time, WhatsApp, SMS, email, number of touches, quality

- ☐ Lighthouse mobile: performance, LCP, CLS, accessibility

- ☐ Schema types present (view source / Rich Results Test)

- ☐ Sitemap size and structure

- ☐ Parent app: store rating, reviews, features

- ☐ Social: followers and posting frequency per platform; YouTube top videos

- ☐ Google Business Profile rating and review count for the nearest campus to Nagarbhavi

## Open questions

- Which local Bengaluru schools near Nagarbhavi does ULL lose families to? Add them to the study.

- Is ULL comfortable showing fee ranges publicly?

# 16. Dedicated pages for ULL Global and ULL Auremont

The full page tree, page templates and content checklist for the two school brands, modelled on what competitors do per school (section 15) and on the brand rules in section 5. Auremont (CBSE, live campus at Nagarbhavi) gets a full admissions section; Global (IB, no campus yet) gets a launching-soon section with a waitlist. 9 Nov – 11 Dec 2026.

### Key actions

- Move the current site pages under /auremont/ with 301 redirects from old paths

- Build brand home, campus, programme, stage and admissions templates in the page builder

- Collect missing Auremont content (story, facilities, fees, faculty, photos, contact, affiliation details)

- Write ULL Global pages (IB approach, leadership, launch plans) with IB-approved wording

- Add School JSON-LD per campus and Organization/subOrganization for the group

- SEO validation, Lighthouse, mobile and accessibility pass on every page before 11 Dec

## What competitors do per school (from section 15)

- VIBGYOR: each campus at /school/{city}/{board}/{campus} with its own enquiry, facilities and gallery.

- Orchids: each campus at /{city}-branches/{campus}, plus city admission pages.

- Ryan: board/city search, some schools on subdomains or separate domains.

ULL has one campus and two brands, so we use brand-level pages for the story and curriculum and campus-level pages for local details (address, fees, transport, visits). This keeps content once per brand and makes a second campus a copy of one page.

## ULL Auremont (/auremont)

Accent: orange. CBSE, Nursery – Grade 10. Motto "Rooted deep. Rising high."

/auremont/                              Brand home
/auremont/about/                        Our story, the name, vision & mission
/auremont/about/the-auremont-way/       Values
/auremont/about/leadership/             Principal, academic heads
/auremont/about/our-teachers/           Faculty profiles
/auremont/academics/                    Approach + Learning Cycle
/auremont/academics/foundational/       Nursery – Grade 2
/auremont/academics/preparatory/        Grades 3 – 5
/auremont/academics/middle/             Grades 6 – 8
/auremont/academics/secondary/          Grades 9 – 10
/auremont/academics/assessment/         Assessment and progress (HPC)
/auremont/sports/                       Sports & fitness (Jonty Rhodes)
/auremont/beyond-the-classroom/         Hub
/auremont/beyond-the-classroom/pulse/  
/auremont/beyond-the-classroom/ruchi/
/auremont/beyond-the-classroom/kushala/
/auremont/beyond-the-classroom/aurora-lab/
/auremont/beyond-the-classroom/summit-pathway/
/auremont/safety-and-care/              CCTV, transport, health, counselling, POCSO policy
/auremont/parents/                      Partnering with parents, a week at Auremont, portal
/auremont/news/  /auremont/events/
/auremont/nagarbhavi/                   Campus page (below)
/auremont/nagarbhavi/facilities/
/auremont/nagarbhavi/gallery/
/auremont/nagarbhavi/virtual-tour/
/auremont/nagarbhavi/transport/         Routes and areas served
/auremont/nagarbhavi/fees/              Fee range per grade band (if approved)
/auremont/nagarbhavi/mandatory-disclosure/  CBSE public disclosure
/auremont/admissions/                   5-step process, timeline, eligibility by age
/auremont/admissions/enquire/
/auremont/admissions/book-a-visit/
/auremont/admissions/faq/
/auremont/admissions/documents/         Documents checklist
/auremont/admissions/brochure/          Download (gated)

### Auremont brand home sections

- Hero video (walkthrough cut) + "Admissions open 2027-28" + Book a visit / Enquire.

- Proof strip: CBSE, Nursery – Grade 10, teacher-student ratio, Jonty Rhodes sports partnership, campus area.

- Four pillars.

- Learning Cycle.

- Stages (4 cards → stage pages).

- Sports.

- Beyond the classroom (5 programme cards).

- Safety and care.

- Campus tour (video + gallery strip).

- Parent stories (video testimonials).

- Teachers (3 profiles + link).

- News and events.

- FAQ (FAQPage schema).

- Visit CTA + map + WhatsApp.

### Campus page /auremont/nagarbhavi/

Address and map, phone/WhatsApp, visiting hours, grades offered, facilities summary, transport areas, fee range, admissions timeline, counsellor contact, Google rating (section 12), "Book a visit" slot picker. JSON-LD School with address, geo, opening hours, parentOrganization: ULL India.

### Auremont content to collect (gaps from PLAN.md and ULL-Auremont-Content-Map.xlsx)

- ☐ Our story, founding year, founders/leadership bios and photos

- ☐ Facilities list with photos (classrooms, labs, library, sports, transport, infirmary)

- ☐ Phone, email, full address and PIN, map pin

- ☐ CBSE affiliation number or status; mandatory disclosure documents

- ☐ Fee ranges by grade band (or decision to hide)

- ☐ Faculty list and photos (with consent)

- ☐ Real photos to replace AI visuals; walkthrough video (section 4)

- ☐ Transport routes and areas

- ☐ Admission timeline and age eligibility for 2027-28

- ☐ Brochure PDF

## ULL Global (/global)

Accent: teal. IB. No campus yet, so status launching.

/global/                         Brand home (launching)
/global/why-ib/                  IB philosophy, learner profile, PYP/MYP/DP explained for parents
/global/our-approach/            How ULL Global will teach (inquiry, languages, global citizenship)
/global/leadership/              Founding head, advisors
/global/faq/                     When, where, fees range expectation, IB status
/global/register-interest/       Waitlist form → CRM (brand=global, intent=waitlist)
/global/news/                    Milestones (site, construction, IB candidacy)

### Global brand home sections

- Hero: "ULL Global, an IB school by ULL India, coming to <city> in <year>" (only once confirmed).

- What IB means for your child (3 cards: PYP, MYP, DP).

- Learner profile (10 attributes).

- Our approach.

- Founding leadership.

- Timeline to opening.

- FAQ.

- Register interest form + "visit ULL Auremont meanwhile" cross-link.

IB wording: until authorised, use only the wording IB allows for interested or candidate schools; do not say "IB World School". Do not use the IB logo without permission.

When a campus is confirmed, add /global/<campus>/ using the same campus template as Nagarbhavi.

## Shared templates (page builder)

| Template | Used by |
| --- | --- |
| Brand home | /auremont/, /global/ |
| Campus | /auremont/nagarbhavi/, future campuses |
| Stage | 4 Auremont stages, future Global programmes |
| Programme | 5 Beyond the classroom pages |
| Admissions step | admissions sub-pages |
| Landing (ads) | campaign pages (no nav, one form) |

New blocks needed: video-hero, stats-strip, faculty-grid, testimonial-video, map-contact, fee-table, timeline, download-gate, news-list, event-list, brand-switcher.

## Acceptance

- Every page in both trees exists, passes SEO validation (section 7), and has a CTA.

- Old root URLs redirect to /auremont/....

- Lighthouse mobile ≥ 90 on brand homes and the campus page.

- Global pages make no claims about IB authorisation, fees or opening dates that are not confirmed.

## Open questions

- ULL Global city and target opening year?

- Show Auremont fees publicly (range) or on request?

- Who signs off copy for each brand?

# 17. Success metrics for each team

Success metrics, targets and a review cadence for the website team, CMS tech team, digital marketing, social media, offline marketing, ground sales, and the three platforms (Google Search Console, Meta Ads, Google Analytics). Targets are starting points for the 2027-28 season and are reset after four weeks of real data. 2 – 13 Nov 2026, then weekly.

### Key actions

- Record baselines for each metric in the first two weeks after launch

- Agree targets with each team lead and the Group admin

- Show every metric on the /admin insights dashboard (section 14) or a shared sheet until it exists

- Weekly 30-minute review, monthly target reset

## North star

Admissions confirmed for 2027-28 at ULL Auremont vs the seat target, and ULL Global waitlist size. Every team metric below should move one of these.

Funnel used by everyone (definitions from sections 8 and 18):

Website visitor → Lead → Contacted → Visit booked → Visited → Application → Admission confirmed → Enrolled

## 1. Website building team

| Metric | Target | Source |
| --- | --- | --- |
| Launch on 14 Dec with all pages in section 16 | 100% of launch pages | Checklist |
| Lighthouse mobile performance (key pages) | ≥ 90 | Lighthouse CI |
| Core Web Vitals (field) | LCP < 2.5s, CLS < 0.1, INP < 200ms for 75% of visits | Search Console CWV report |
| Visitor → lead conversion rate | ≥ 3% (landing pages ≥ 8%) | GA4 + CRM |
| Form completion rate (start → submit) | ≥ 60% | GA4 events |
| Uptime | ≥ 99.9% | Route 53 health check |
| Accessibility | WCAG 2.1 AA, 0 critical issues | axe |
| Broken links / 404s | 0 internal | Crawl |

## 2. CMS tech team

| Metric | Target | Source |
| --- | --- | --- |
| Time from AI draft to published page (no developer) | < 30 min | CMS versions |
| Pages published by content team without dev help | 100% | Audit |
| Publish → live on site | < 5 min | Deploy logs |
| Pages passing SEO validation at publish | 100% (enforced) | Section 7 |
| CRM lead ingestion latency | < 1 min | Logs |
| Sync failures to external CRM (section 19) | < 0.5%, retried within 1h | Outbox |
| Deploy success rate | ≥ 95% | GitHub Actions |
| P1 bug fix time | < 24h | Issue tracker |
| Restore drill passed | Monthly | Runbook |

## 3. Digital marketing team

| Metric | Target (start) | Source |
| --- | --- | --- |
| Cost per lead (CPL) | Set after 4 weeks; Bengaluru school CPL is typically several hundred rupees | Ads + CRM |
| Cost per visit | Track; aim ≤ 4× CPL | CRM |
| Cost per admission | Main metric; target from budget ÷ seats | Section 14 |
| Lead → visit rate | ≥ 25% | CRM |
| Share of leads with a valid source | 100% | Section 18 |
| Search impression share (brand + local terms) | ≥ 70% | Google Ads |
| Landing page conversion | ≥ 8% | GA4 |

## 4. Social media team

| Metric | Target | Source |
| --- | --- | --- |
| Posting plan delivered (section 4 cadence) | ≥ 90% | Calendar |
| Engagement rate (Instagram) | ≥ 3% | Meta |
| Follower growth | +15% per month during season | Meta, YouTube |
| Reel views (local reach) | Track; grow month on month | Meta |
| Profile → website taps | Track | Instagram |
| Leads with source = organic social | Track; grow month on month | CRM |
| Aftermovie published after an event | ≤ 72h | Calendar |
| Response time to comments and DMs | < 2h in working hours | Meta inbox |

## 5. Offline marketing team

| Metric | Target | Source |
| --- | --- | --- |
| Activations run per month (societies, preschools, workshops) | ≥ 8 | Event log |
| Leads per activation (QR/coupon) | ≥ 15 | CRM |
| Cost per lead by activity (hoarding, stall, insert) | Compare with digital CPL | Spend + CRM |
| QR scans → leads | ≥ 30% | Short links |
| Coupon redemption | Track | CRM |
| Open house attendance vs RSVPs | ≥ 60% | Visitor desk |

## 6. Ground sales team (counsellors, tele-callers, front desk)

| Metric | Target | Source |
| --- | --- | --- |
| First response time | < 15 min in working hours | CRM SLA |
| Contact rate within 24h | ≥ 90% | CRM |
| Lead → visit | ≥ 25% | CRM |
| Visit → application | ≥ 50% | CRM |
| Application → admission | ≥ 60% | CRM |
| Visit no-show rate | < 20% | Section 6 |
| Average wait time at reception | < 10 min | Section 6 |
| Follow-ups done on time | ≥ 95% | Tasks |
| Conversation quality score | ≥ 75/100 | Section 21 |
| Lost reason recorded | 100% | CRM |

## 7. Google Search Console

| Metric | Target | Notes |
| --- | --- | --- |
| Indexed pages vs submitted | ≥ 95% | Pages report |
| Clicks (non-brand) | Grow month on month | Exclude "ULL" queries |
| Average position for target terms ("CBSE school Nagarbhavi", "school near Vijayanagar", "best school RR Nagar") | Top 10 within 3 months, top 3 within 6 | Performance |
| CTR on top pages | ≥ 4% | Improve titles/meta |
| Core Web Vitals "good" URLs | 100% |  |
| Rich results valid (FAQ, Breadcrumb, Event) | 0 errors | Enhancements |

## 8. Meta Ads

| Metric | Target | Notes |
| --- | --- | --- |
| CTR (link) | ≥ 1% |  |
| CPM | Track | Local radius |
| Lead form completion → valid lead (phone reachable) | ≥ 70% | Use qualifying question |
| CPL and cost per visit | See section 3 |  |
| Frequency | ≤ 3 per week | Rotate creatives |
| Conversions API event match quality | ≥ 6/10 | Events Manager |

## 9. Google Analytics (GA4)

| Metric | Target | Notes |
| --- | --- | --- |
| Tracking coverage: enquiry_submitted, visit_booked, brochure_download, whatsapp_click, call_click | 100% of forms and CTAs | Tag tests |
| Engaged session rate | ≥ 55% |  |
| Conversion rate by source/medium | Reported weekly |  |
| Consent rate | Track | Consent Mode v2 |
| GA4 vs CRM lead count gap | < 10% | Data quality |

## Review cadence

| When | Who | What |
| --- | --- | --- |
| Daily 10:00 | Counsellors + School admin | Yesterday's leads, SLA breaches, today's visits |
| Weekly, Friday | All team leads | These metrics, three actions |
| Monthly | Group admin | Cost per admission by channel, budget shift, target reset |
| End of season | All | What worked, budget for next year |

## Open questions

- Seat target per grade for 2027-28?

- Total marketing budget for the season, to set cost-per-admission targets?

# 18. CRM lead source attribution (online, offline, coupons, WhatsApp)

Every lead records where it came from, whatever the channel, including website forms, ads, lead forms, WhatsApp messages, phone calls, walk-ins, offline QR codes, coupons, referrals, school directories and events. We use one source taxonomy, first-touch and last-touch attribution, and every touch on the lead's timeline. 16 Nov – 18 Dec 2026.

### Key actions

- Agree the source taxonomy (channel → source → campaign → content) and UTM conventions

- Capture UTM, gclid, fbclid, referrer, landing page and first-visit time in a first-party cookie and send them with every form

- Add webhooks for Meta Lead Ads, Google Ads lead forms, WATI (WhatsApp) and the telephony provider

- Build a short-link and QR generator plus coupon codes in /admin for offline campaigns

- Require source on manual entries (walk-ins, events, referrals)

- Source and campaign reports with funnel conversion and cost per stage

## Source taxonomy

Four levels on every touch: channel → source → campaign → content.

| Channel | Sources (examples) | How it is captured |
| --- | --- | --- |
| paid_search | google_ads | UTM + gclid |
| paid_social | meta, youtube, linkedin | UTM + fbclid; Meta Lead Ads webhook |
| organic_search | google, bing | Referrer, no UTM |
| organic_social | instagram, facebook, youtube, linkedin | UTM on bio links (?utm_source=instagram&utm_medium=bio) |
| local | google_business_profile | UTM on the GBP website link (utm_source=gbp) + GBP call tracking |
| direct | – | No referrer, no UTM |
| referral_site | edustoke, schoolmykids, justdial, sulekha, news sites | Referrer domain or partner UTM; directory lead emails/APIs parsed |
| whatsapp | click_to_chat, broadcast, inbound | Prefilled message with a ref code; WATI webhook |
| phone | ivr_number_<n> | One virtual number per channel (website, hoarding, newspaper); telephony webhook |
| walk_in | gate | Visitor desk (section 6), source question at the gate |
| offline | hoarding, society_stall, preschool, pamphlet, newspaper, radio, event | Unique short link + QR per placement; coupon code |
| referral | parent, staff, alumni, preschool_partner | Referral code per referrer |
| event | open_house, workshop, sports_clinic | Event registration form |
| email | newsletter, nurture | UTM on every email link |
| ai_voice | sarvam_inbound, sarvam_outbound | Section 22 |

UTM rules: lowercase, underscores, utm_campaign=<brand>_<yyyymm>_<name> (e.g. auremont_202612_admissions_open). A UTM builder in /admin creates links so nobody types them by hand.

## Website capture

Fields sent with every form: utm_source, utm_medium, utm_campaign, utm_content, utm_term, gclid, fbclid, referrer, landing_page, first_visit_at, page_url, plus first-touch copies of the same. The cookie is first-party and set only after analytics consent; without consent we still store the UTM of the current visit on the form (that is the user's own action, not tracking).

The current Enquiries field source becomes a group attribution with first touch, last touch and touches[].

## Connectors

| Connector | Endpoint | Notes |
| --- | --- | --- |
| Meta Lead Ads | /api/hooks/meta-leads | Subscribe the page to leadgen webhooks; fetch the lead by id with the system user token; map form fields; source = paid_social/meta with campaign, ad set, ad ids |
| Google Ads lead form assets | /api/hooks/google-leads | Webhook URL + key configured in Google Ads; includes gcl_id, campaign id |
| WATI (WhatsApp) | /api/hooks/wati | Inbound message from an unknown number → new lead; the prefilled text "Hi, I'm interested in admissions [ref: HRD-NGB-07]" sets the source; known number → touch on the existing lead |
| Telephony (Exotel / Knowlarity / Ozonetel) | /api/hooks/calls | Virtual number dialled → source; call recording link stored |
| Directories (Edustoke etc.) | Email parser (SES inbound → S3 → Lambda) or partner API | Source = referral_site/<name> |
| Sarvam AI | /api/hooks/sarvam | Section 22 |

All webhooks verify signatures, are idempotent (dedupe by provider event id) and go through the SQS queue (section 2).

## Offline: QR, short links and coupons

- /admin/campaigns/links: create a placement (e.g. "Hoarding, Nagarbhavi Circle, Dec 2026"), get a short link ullindia.com/go/ngb-circle and a printable QR (SVG/PNG). The short link redirects to the landing page with UTMs and logs the scan (count, time, device).

- Coupon codes: /admin/campaigns/coupons with code, campaign, benefit (e.g. waived registration fee, early-bird), validity, max uses. Entered on the enquiry form ("Have a code?") or by the counsellor. Redemption tracked against the lead and the admission.

- Referral codes: one per enrolled family/staff/partner preschool, auto-generated; referral reward tracked on admission.

- Printed brochures and pamphlets each carry a placement-specific QR.

## Attribution rules

- First touch = how the family first found us (marketing credit for awareness).

- Last touch before lead = what converted them into a lead.

- All touches kept on the timeline (e.g. Instagram → Google search → walk-in).

- Reports show first and last touch side by side; a simple position-based model (40/20/40) later if wanted.

- A walk-in who first came through a hoarding QR keeps the hoarding as first touch; the gate question "How did you hear about us?" is stored as a self-reported touch.

- Duplicate leads (same phone) add a touch, not a new lead (section 8).

- Offline conversions upload: visits and admissions are sent back to Google Ads (by gclid) and Meta (Conversions API, hashed phone/email) so the ad platforms optimise for real visits, not form fills.

## Reports

- Leads, visits, applications, admissions by channel / source / campaign / placement, first vs last touch.

- Cost per lead / visit / admission where spend is known (ad APIs, section 14; offline spend entered per campaign).

- Coupon and referral performance.

- "Unknown source" share (target < 5%).

## Acceptance

- A test lead from each channel in the table lands in the CRM with the right channel and source.

- A QR scan, a coupon and a referral code each show up on the lead.

- Visits and admissions flow back to Google Ads and Meta.

## Open questions

- Which telephony provider (or existing numbers) does the school use today?

- Which school directories does ULL list on, and do they send leads by email or API?

- Coupon benefits allowed for 2027-28?

# 19. External CRM sync (Orggen CRM / Zoho CRM)

Every lead is saved first in ULL's own database (the system of record). A sync layer then mirrors leads, stage changes and activities to an external CRM (Orggen CRM or Zoho CRM) for communication and other uses, and takes back the few fields that CRM owns. One adapter per CRM, an outbox for reliability, and field mapping configured in /admin. 4 – 22 Jan 2027.

### Key actions

- Confirm which external CRM is used first (Orggen or Zoho) and what it is for (campaigns, telecalling, reporting)

- Get API docs, sandbox credentials and the field list for the chosen CRM (Orggen API to be confirmed from their docs)

- Build an outbox table and SQS worker that pushes changes with retries and dead-lettering

- Write the Zoho adapter (REST v8, OAuth) and the Orggen adapter behind one interface

- Field and stage mapping screen in /admin; per-campus enable switch

- Receive webhooks for the fields the external CRM owns (e.g. call disposition) and write them back as activities

- One-time backfill of existing leads with a dry run

## Principle

Website / ads / WhatsApp / walk-in  ──►  ULL database (Payload + Postgres)  ──►  External CRM
                                         system of record                       mirror for communication

- Our database is written first, always. If the external CRM is down, nothing is lost; the outbox retries.

- Each field has one owner. Conflicts are resolved by ownership, not by "last write wins".

## Field ownership

| Field | Owner | Direction |
| --- | --- | --- |
| Family, child, contact details, consent | ULL | → external |
| Brand, campus, grade, academic year | ULL | → external |
| Source and attribution (section 18) | ULL | → external |
| Stage | ULL | → external (external stage changes come back as a suggestion activity, or are accepted if configured) |
| Owner (counsellor) | ULL | → external (mapped to external user) |
| Activities: calls, WhatsApp, visits, AI summaries | ULL | → external as notes/tasks |
| Call disposition / campaign membership from the external CRM | External | ← back as activities |
| External record id | External | ← stored on the family/lead |

## Architecture

- syncOutbox(entity, entityId, op, payloadHash, target, attempts, nextAttemptAt, status).

- Retries with backoff: 1 min, 5 min, 30 min, 2 h, 12 h, then dead-letter with an alert to the tech owner.

- Idempotent upsert keyed by our id (stored in a custom external field ull_id) and the verified phone number.

- Rate limiting per provider (Zoho API credits per day depend on the edition).

- A Sync status badge on each lead (synced, pending, failed + retry button).

## Adapter interface

### Zoho CRM

- OAuth 2.0 server-based app (India data centre accounts.zoho.in, API www.zohoapis.in), refresh token in Secrets Manager.

- Modules: Contacts (parent), Leads or Deals (admission per child per year), Notes / Tasks / Calls (activities). Recommended: Contacts + Deals, with the Deal pipeline mirroring our stages.

- Custom fields: ull_id, brand, campus, grade, academic_year, first_touch_source, last_touch_source, utm_campaign, coupon_code.

- Upsert API with duplicate check on ull_id then Phone.

- Inbound: Zoho workflow rules → webhook to /api/hooks/crm/zoho (signed with a shared secret in a header), or Notification API.

### Orggen CRM

- API surface, auth and webhook support to be confirmed from Orggen's documentation (not public to us yet).

- Same interface; if Orggen has no upsert, the adapter does search-by-phone then create/update.

- If Orggen has no webhooks, poll changed records every 10 minutes.

## Mapping screen (/admin/integrations/crm)

- Enable per CRM and per campus.

- Stage mapping table (our stage → their stage/pipeline).

- User mapping (counsellor email → external user id).

- Field mapping with test ("send a sample lead to sandbox").

- Last 100 sync events with payloads (PII masked).

## Privacy

- Only send what the external CRM needs; children's data minimised (name, grade, DOB optional).

- Consent flags travel with the contact; marketing opt-outs must be honoured there too.

- A data processing agreement with the CRM vendor (DPDP).

- Deleting/anonymising a family in ULL triggers deletion in the external CRM.

## Acceptance

- A new website lead appears in the external CRM within 1 minute.

- Stopping the external API for an hour loses nothing; all changes catch up.

- A disposition set in the external CRM appears on the ULL timeline.

- Sync failure rate < 0.5% (section 17).

## Open questions

- Orggen or Zoho first? Is one already in use with existing data?

- Zoho edition (affects API credits and custom modules)?

- Should external stage changes be accepted automatically?

# 20. ULL India on aptitudetest.in (ullindia.aptitudetest.in)

A ULL-branded psychometric assessment portal at ullindia.aptitudetest.in for Aptitude, Interest, IQ, Learning Style, MMPI, DMIT, Career test, College predictor and Stream selector. Students and parents launch tests from their ULL dashboards with single sign-on, and see test status and reports there. Implementation follows the integration documentation aptitudetest.in will provide; this plan sets the checklist of what is covered and what is not. 11 Jan – 19 Feb 2027.

### Key actions

- Receive the aptitudetest.in integration docs (SSO, APIs, webhooks, report formats, sandbox)

- aptitudetest.in team creates ullindia.aptitudetest.in with ULL branding (logo, colours, support contacts)

- Agree which tests are offered to whom, pricing (free for enrolled students vs paid lead magnet), and GST treatment (section 3)

- Implement the SSO handoff from the ULL portal (section 9)

- Receive test status webhooks and store assessments per child

- Fetch report PDFs and key scores into the private bucket and show them in both dashboards

- Create CRM leads and activities from test sign-ups by non-enrolled families

- Keep the coverage checklist below up to date as each item is built and tested

## Who uses it, and why

| User | Purpose |
| --- | --- |
| Enrolled students (Grades 6–10 at Auremont) | Learning style, interest, aptitude, stream selector (Grade 10), career test; part of the student dashboard (section 10) |
| Parents | See reports and counsellor recommendations (section 11) |
| Prospective families | Free or low-cost test as a lead magnet ("Find your child's learning style"); creates a CRM lead (section 18 source aptitudetest) |
| Counsellors | Use reports in counselling sessions and stream guidance |

## Tests

| Test | Typical audience | Notes |
| --- | --- | --- |
| Aptitude | Grades 8–12 | Stream and career guidance |
| Interest | Grades 8–12 | Career clusters |
| IQ | Any | Present carefully to parents; never as a label |
| Learning style | Grades 1–10 | Good for parents of younger children |
| MMPI | Adults / older adolescents | Clinical personality inventory; use only with a qualified psychologist and only where clinically justified. Not a school marketing tool. Confirm age suitability with aptitudetest.in |
| DMIT | Any | Dermatoglyphics (fingerprint-based) tests are not supported by scientific evidence. Recommend ULL does not promote DMIT under the ULL brand, or presents it only with a clear disclaimer. Decision for ULL leadership |
| Career test | Grades 9–12 |  |
| College predictor | Grades 11–12 | Limited use at Auremont (up to Grade 10) |
| Stream selector | Grade 10 | Science / Commerce / Humanities |

## Integration (subject to their docs)

### Data stored in ULL

assessments: child, test type, provider order id, status (invited, started, completed, report_ready, expired, cancelled), invited/started/completed dates, report file (private bucket, section 13), key scores (JSON), counsellor notes, shared-with-parent flag.

### What the dashboards show

- Student (section 10): tests available, in progress (resume link), completed, report summary in plain language.

- Parent (section 11): same per child + full PDF + "Book a counsellor session to discuss".

- Counsellor (section 8): reports on the lead/student timeline.

## Coverage checklist

Legend: ✅ covered in this plan · 🟡 depends on aptitudetest.in docs · ❌ not covered / out of scope

| # | Item | Status | Notes |
| --- | --- | --- | --- |
| 1 | Subdomain ullindia.aptitudetest.in set up and branded | 🟡 | Their DNS and hosting; ULL supplies logo, colours, support email/phone |
| 2 | SSL on the subdomain | 🟡 | Their wildcard cert presumably |
| 3 | SSO from ULL portal (no second login) | 🟡 | Method (JWT / OIDC / SAML) per docs; section 9 |
| 4 | Account creation on first launch (just-in-time provisioning) | 🟡 | Needs their user API or SSO auto-provisioning |
| 5 | Test catalogue per grade, shown in ULL dashboards | ✅ | Configured in ULL CMS |
| 6 | Launch / resume test from the dashboard | 🟡 | Needs a resume URL |
| 7 | Status webhooks (started, completed, report ready) | 🟡 | Else poll their API every 15 min |
| 8 | Report PDF download into ULL private storage | 🟡 | Needs report API |
| 9 | Key scores as structured data | 🟡 | For dashboards and metrics |
| 10 | Status and reports in student dashboard | ✅ | Section 10 |
| 11 | Status and reports in parent dashboard | ✅ | Section 11 |
| 12 | Report-ready notification (WhatsApp/email) | ✅ | ULL notify() adapter |
| 13 | CRM lead for non-enrolled sign-ups with source aptitudetest | ✅ | Section 18 |
| 14 | Counsellor view of reports | ✅ | Section 8 |
| 15 | Bulk invite a whole grade | 🟡 | Needs bulk API or CSV upload on their side |
| 16 | Payments for paid tests | 🟡 | Their checkout, or ULL gateway (section 3); decide |
| 17 | Parental consent before a minor takes a test | ✅ | Captured in ULL before launch (section 9) |
| 18 | Data processing agreement and DPDP compliance | ✅ | To sign with aptitudetest.in |
| 19 | Data deletion when a family asks | 🟡 | Needs their delete API or a manual process |
| 20 | Reporting: tests taken, completion rate, reports viewed | ✅ | ULL side from assessment records |
| 21 | Psychologist review for MMPI | ❌ | Clinical process, outside the software |
| 22 | DMIT kit / fingerprint capture | ❌ | Hardware and scientific validity concerns; recommend not offered under ULL brand |
| 23 | Offline / paper tests | ❌ | Not planned |
| 24 | Native mobile app | ❌ | Web only |

## Acceptance

- A Grade 9 student launches a test from the ULL dashboard without a second login, completes it, and sees the report there within the time aptitudetest.in promises.

- The parent gets a WhatsApp when the report is ready.

- A prospective family taking a free test appears in the CRM with source aptitudetest.

## Open questions

- When will the integration docs and sandbox be ready?

- Which tests are free for enrolled students, and which are paid?

- ULL's position on DMIT and MMPI.

# 21. Audio recorder devices and AI success metrics per persona

Choose and deploy recording devices for sales, marketing, teachers and counsellors; transcribe and analyse conversations with AI; and score each persona against its own success metrics. Consent and retention are built in from the start. Pilot 18 Jan – 26 Feb 2027 with counsellors at Nagarbhavi, then sales, then teachers.

### Key actions

- Trial two or three devices for a week each (wearable AI recorder, lapel mic + phone app, desk mic for classrooms)

- Approve consent notices, opt-out flow and retention periods per persona (DPDP Act); teacher recordings agreed with staff

- Build upload → transcription (Sarvam, AWS Transcribe fallback) → diarisation → Claude analysis → scorecard

- Define and calibrate rubrics for each persona with their managers

- Persona dashboards and coaching views in /admin

- Pilot counsellors, then sales, marketing, then teachers (opt-in)

## Devices

| Option | Example | Fits | Pros | Cons |
| --- | --- | --- | --- | --- |
| Wearable AI recorder | Plaud NotePin / Plaud Note, similar clip-on recorders | Counsellors, sales | Small, all-day battery, one-tap, app syncs to phone; exports audio | Vendor cloud by default; we must export audio to our bucket, not rely on their transcripts |
| Lapel mic + company phone app | Wireless lavalier (e.g. Boya/Rode class) with a ULL recording app (PWA or simple Android app) | Counsellors, sales | Audio goes straight to our bucket; tied to the visit in the CRM | Phone must be with the person |
| Desk / boundary mic | USB conference mic in counselling rooms | Counselling room | Always ready, good two-person audio | Fixed location |
| Classroom mic | Ceiling or teacher lapel mic | Teachers (opt-in) | Lesson analysis | Many voices, children's voices = higher privacy bar |

Recommendation: pilot with lapel mic + ULL recording app for counsellors (data stays in ULL's AWS, auto-linked to the visit) and one wearable recorder for comparison. Desk mics in the counselling rooms. Teachers only later, opt-in, and analysing the teacher's voice track only.

Selection test (one week each): audio quality in a noisy reception, battery for a 9-hour day, sync reliability, export to S3, cost per unit, and how counsellors feel wearing it.

## Pipeline

- Linking: the app records against a visit/lead/class id; device uploads are matched by user + time window.

- Languages: English, Kannada, Hindi and code-mixed speech (Sarvam handles Indian languages well; keep a 50-recording accuracy test set).

- Analysis model: claude-sonnet-5-5 with a rubric per persona and structured output; claude-haiku-5-5 for quick tagging.

- Every score has quoted evidence from the transcript, so managers can check it.

- Cost tracked per recording (STT minutes + tokens).

## Consent and retention

- Parents: notice at reception + spoken line at the start; "No recording" button (section 6).

- Staff: written policy and agreement; purpose is coaching and service quality, not covert surveillance; staff can see their own recordings and scores.

- Children: no recording of children in counselling without parental consent; classroom analysis uses the teacher's voice only.

- Retention: audio 180 days, transcripts 1 year, scores kept (no audio) for performance history. Configurable.

- Access: the person, their manager, School admin. Every playback logged.

## Success metrics per persona

### Counsellor (admissions counselling sessions)

| Metric | How AI measures it | Target |
| --- | --- | --- |
| Discovery: asked about the child's needs, interests, current school, family priorities | Rubric checklist | ≥ 4 of 5 |
| Talk ratio (counsellor vs parent) | Speaker time | 40–60% |
| Key points covered (curriculum, safety, sports, fees, transport, next steps) | Checklist | ≥ 80% |
| Objections raised and handled (fees, distance, new school, board) | Detection + quality | Handled ≥ 80% |
| Unanswered questions | Detection | Logged → content/training |
| Clear next step agreed (interaction date, documents) | Detection | ≥ 90% |
| Tone and empathy | Rubric 1–5 | ≥ 4 |
| Session → application conversion | CRM | ≥ 50% |

### Sales (tele-callers, ground sales)

| Metric | Measure | Target |
| --- | --- | --- |
| Opening: name, school, purpose in 15 seconds | Detection | ≥ 90% |
| Qualification (grade, area, timeline, decision-maker) | Checklist | ≥ 3 of 4 |
| Visit booking ask made | Detection | 100% of qualified calls |
| Visit booked rate | CRM | ≥ 30% of connected calls |
| Compliance: no false claims, no pressure, opt-out honoured | Detection | 100% |
| Average handle time | Duration | Track |
| Sentiment at end of call | AI | Positive/neutral ≥ 80% |

### Marketing (events, society stalls, open houses, parent interviews for content)

| Metric | Measure | Target |
| --- | --- | --- |
| Message consistency (brand pillars mentioned correctly) | Checklist vs facts sheet | ≥ 90% |
| Parent questions and themes (top 10 per month) | Topic clustering | Feeds content plan |
| Competitor mentions (which schools, why) | Detection | Feeds section 15 |
| Leads captured per activation with source | CRM | Section 17 |
| Testimonial-worthy quotes found (with consent) | Detection | ≥ 5 per month |

### Teacher (opt-in, coaching only)

| Metric | Measure | Target |
| --- | --- | --- |
| Teacher talk vs student talk time | Speaker time (teacher track + classroom mic) | Student talk ≥ 30% |
| Open questions asked | Detection | Grow over term |
| Wait time after questions | Audio gaps | ≥ 3 s |
| Lesson structure (objective stated, recap, check for understanding) | Checklist | ≥ 80% |
| Praise vs correction balance | Detection | Track |
| Use of student names / inclusive participation | Detection | Track |

Teacher scores are never used for appraisal without the academic head and staff agreeing; they are for self-reflection and coaching.

## Dashboards

- Personal: my sessions, scores over time, best moments, one tip per week.

- Manager: team averages, calibration (manager rates 5 sessions/month to check the AI), coaching queue.

- Group admin: top objections, unanswered questions, competitor mentions, conversion vs quality score correlation.

## Rollout

| Weeks | Step |
| --- | --- |
| 18 Jan – 29 Jan | Device trial, consent approved, pipeline on UAT |
| 1 Feb – 12 Feb | Counsellor pilot (Nagarbhavi), calibration |
| 15 Feb – 26 Feb | Sales and tele-callers; marketing events |
| From Apr (new year) | Teachers, opt-in |

## Acceptance

- A recorded counselling session shows a transcript, summary and scorecard on the visit within 15 minutes of upload.

- Manager and AI scores agree within 1 point (5-point scale) on ≥ 80% of calibration samples.

- No recording exists without a consent record.

## Open questions

- How many devices in the pilot (counsellors, tele-callers)?

- Do staff have company phones?

- Union/staff policy considerations for teacher recordings?

# 22. Sarvam AI voice agents (outbound and common inbound with human handover)

AI voice agents built on Sarvam AI for outbound calls (fee reminders, lead follow-up, visit reminders, re-engagement) and a common inbound support number (desk admin, online counsellor), in English, Kannada and Hindi, with handover to a real person. The goal is to keep the operations team as small as possible. Every call is logged in the CRM. 1 Feb – 26 Mar 2027.

### Key actions

- Choose the telephony partner (Exotel / Ozonetel / Knowlarity / Plivo) for numbers, SIP and live transfer; get DLT and calling-number registrations done

- Set up the Sarvam account and agent platform; confirm voices, languages, latency, pricing and telephony integration

- Expose CRM tools to the agent (look up family, fees due, book visit, create callback, send WhatsApp, hand over)

- Build agents one use case at a time, starting with visit reminders and inbound FAQ, then fee reminders and lead follow-up

- Warm transfer to a human with a context summary; after-hours callback booking

- Calling windows, consent, opt-out, disclosure that the caller is an AI, recording notice

- Test sets per use case, weekly review of 50 calls, metrics in section 17

## Why Sarvam

Sarvam's models are built for Indian languages: speech-to-text (Saarika) handles code-mixed Kannada/Hindi/English, text-to-speech (Bulbul) has Indian voices, and their conversational agent platform (Samvaad) connects to telephony. Confirm current product names, pricing and SLAs with Sarvam during setup.

## Architecture

### Tools the agent can call (server-side, authenticated, logged)

| Tool | Purpose |
| --- | --- |
| lookupCaller(phone) | Family, children, open leads, enrolled status, language preference |
| getFeesDue(familyId) | Amount, due date, payment link (section 3) |
| sendPaymentLink(familyId) | WhatsApp/SMS the link |
| getVisitSlots(campus, date) / bookVisit(...) | Book or move a visit (section 6) |
| answerFaq(question) | Retrieval over the CMS FAQ library and brand facts sheet (section 7) |
| createCallback(reason, time) | Task for a human (section 8) |
| logOutcome(disposition, summary) | CRM activity |
| handover(team, summary) | Warm transfer |
| optOut(channel) | Stop calls/messages |

The agent never reads out sensitive data until the caller is verified (calling from the registered number + child's name/DOB check).

## Use cases

### Outbound

| Use case | Trigger | Goal | Hand over when |
| --- | --- | --- | --- |
| Visit reminder / confirm | 24h before a booked visit | Confirm, reschedule, share directions | Caller wants to talk about admissions in detail |
| New lead first call (outside working hours) | Lead created after 19:00 or on Sunday | Qualify (grade, area, timeline), book a visit | Parent asks for a counsellor |
| Post-visit follow-up | +3 days after visit (section 6) | Answer questions, book child interaction | Any objection on fees or a complaint |
| Lead re-engagement | No activity 14 days | Revive or close as lost with reason | Interest shown |
| Fee collection reminder | 7 days before due, on due date, +3, +10 days | Remind, send payment link, note promise-to-pay date | Dispute, hardship, angry caller |
| Document reminder | Documents pending 5 days | List missing documents, send upload link | Questions about eligibility |
| Event invites | Open house, workshop | RSVP | – |
| Upsell / brand recall | Enrolled families (opt-in) | Transport, after-school programmes, sports academy, psychometric tests (section 20) | Interest shown |
| Feedback survey | After first month, after PTM | NPS + one open question | Low score → callback by School admin |

### Inbound (one common number for ULL India)

| Role | Handles |
| --- | --- |
| Desk admin | Routing by brand/campus, school timings, address and directions, holidays, transport routes, "speak to the class teacher" message taking |
| Online counsellor | Admissions FAQs, eligibility by age, curriculum, fee range (only what the CMS allows), book a visit, brochure on WhatsApp |
| Parent support | Fee status and payment link, absence reporting, PTM booking, report-ready questions |
| After hours | Everything above, plus callback booking for anything it can't resolve |

## Human handover

- Warm transfer in working hours: the agent says "I'll connect you to Ms. Priya from admissions", the telephony partner bridges the call, and the human sees a summary pop-up in the CRM (caller, intent, what was said, sentiment).

- Handover triggers: caller asks for a human, two failed understanding attempts, complaint/anger, safety or child-protection concern (immediate, to the School admin), payment dispute, anything not in the tools.

- No human free: create a callback task with an SLA of 30 minutes; tell the caller when to expect it.

- Every handover reason is tagged, so the agent can be improved.

## Compliance

- TRAI / DLT: register the entity, headers and templates; use the number series and registrations required for service vs promotional calls; promotional calls only to consenting numbers not on DND.

- Calling window: 09:00–21:00 IST; no calls on major holidays for non-urgent cases.

- Disclosure at the start: the caller is told it's an AI assistant from ULL and that the call is recorded.

- Consent and opt-out: "Say 'stop calling' at any time"; opt-out is stored and honoured on all channels (section 8).

- Fee calls: polite, factual, no threats; maximum 4 attempts per due cycle.

- DPDP: purpose limitation, recordings retained 180 days (section 21).

## Staffing effect (target)

| Function | Today (typical) | With agents |
| --- | --- | --- |
| Front office phone | 2 people | 1 person for handovers + walk-ins |
| Tele-callers for leads | 2–3 | 1 (qualified handovers only) |
| Fee follow-up | Accounts staff calls | Agent + accounts for disputes |
| After-hours coverage | None | 24×7 |

## Metrics (feed section 17)

| Metric | Target |
| --- | --- |
| Containment (resolved without a human) for inbound FAQ | ≥ 60% |
| Handover with correct summary | ≥ 95% |
| Visit reminder confirmation rate | ≥ 70% |
| Visits booked by agent per week | Track |
| Fee collected within 7 days of reminder | ≥ 60% |
| Caller satisfaction (post-call 1–5) | ≥ 4.0 |
| Average latency (turn response) | < 1.5 s |
| Opt-out rate | < 3% |
| Cost per call vs human cost | Track |

## Build order

| Weeks | Step |
| --- | --- |
| 1 Feb – 12 Feb | Telephony + DLT, Sarvam account, CRM tools API, test number |
| 15 Feb – 26 Feb | Visit reminders (outbound) + inbound FAQ desk (English) |
| 1 Mar – 12 Mar | Lead follow-up and post-visit calls; Kannada and Hindi |
| 15 Mar – 26 Mar | Fee reminders (ready for 2027-28 first term), handover polish, dashboards |

## Acceptance

- A parent calling the common number in Kannada gets school timings and a visit booked without a human.

- A fee reminder call sends a working payment link on WhatsApp during the call.

- A handover shows the summary to the human before they say hello.

- Every call has a CRM activity with disposition and recording link.

## Open questions

- Existing phone numbers to keep, or new numbers?

- Fee reminders from the start of 2027-28, or earlier for the current year?

- Which voices (gender, accent) represent ULL best? Test with parents.

# Appendix A. Decisions needed from ULL India

Each item also appears at the end of its section. Answers can be written straight into this table.

| Section | Decision or information needed |
| --- | --- |
| 2. AWS deployment (infra, CDK, domain, DNS, SSL, CDN, backups) | Who is the registrar and who holds the login? |
| 2. AWS deployment (infra, CDK, domain, DNS, SSL, CDN, backups) | Is email already on the domain (Google Workspace or Microsoft 365)? Microsoft 365 is likely if Entra ID SSO is wanted (section 9). |
| 2. AWS deployment (infra, CDK, domain, DNS, SSL, CDN, backups) | Is a Hyderabad DR copy wanted for prod, or is same-region versioning enough? |
| 3. GST, company profile and payment details | Which entity collects school fees today, and through which bank or gateway? |
| 3. GST, company profile and payment details | Does ULL want online fee collection in 2027-28, or only lead capture this season? |
| 3. GST, company profile and payment details | Is a registration fee planned for 2027-28 admissions? |
| 4. Marketing, online and offline | Monthly media budget for Dec–Mar? |
| 4. Marketing, online and offline | Is the Jonty Rhodes association cleared for ads (image rights, duration)? |
| 4. Marketing, online and offline | Does ULL Global have a launch year and city yet? |
| 5. Brand architecture (ULL India, ULL Global, ULL Auremont) | Is ULL Global's first campus planned (city, year)? Is IB candidacy started? |
| 5. Brand architecture (ULL India, ULL Global, ULL Auremont) | Should Auremont's campus page be /auremont/nagarbhavi now, even with one campus? (Recommended: yes, so a second campus needs no URL changes.) |
| 5. Brand architecture (ULL India, ULL Global, ULL Auremont) | Final logo files (SVG) for each lockup. |
| 6. Visitor management dashboard and operational intelligence | How many entrances does the Nagarbhavi campus have, and is there a guard post with a phone or tablet? |
| 6. Visitor management dashboard and operational intelligence | Does ULL use Google Workspace (Gmail API follow-ups from the counsellor's own mailbox) or Microsoft 365? |
| 6. Visitor management dashboard and operational intelligence | Apollo plan and credits budget per month? |
| 7. Website with CMS, AI content intake and SEO validation | Will writers use Claude, ChatGPT, or both? (Both are supported; the prompt pack is the same.) |
| 7. Website with CMS, AI content intake and SEO validation | Who approves content (one approver per brand)? |
| 7. Website with CMS, AI content intake and SEO validation | Are Kannada pages wanted for 2027-28? |
| 8. In-house CRM for group admins, school admins and counsellors | How many counsellors and tele-callers at launch? |
| 8. In-house CRM for group admins, school admins and counsellors | Are seat targets per grade available for 2027-28? |
| 8. In-house CRM for group admins, school admins and counsellors | Is there an existing spreadsheet of leads to import? |
| 9. SSO for admins (Microsoft Entra ID) and for parents and students | Is ULL on Microsoft 365 (Entra ID tenant exists) and who is the tenant admin? |
| 9. SSO for admins (Microsoft Entra ID) and for parents and students | Do students get school email accounts (Google or Microsoft)? |
| 9. SSO for admins (Microsoft Entra ID) and for parents and students | Will aptitudetest.in accept OIDC, a signed JWT, or SAML? |
| 10. Student dashboard | Which ERP/LMS does ULL Auremont use, and does it have an API? |
| 10. Student dashboard | Does the academic team want HPC-style reports generated from this system? |
| 10. Student dashboard | Are students given devices or school accounts? |
| 11. Parent dashboard | Weekly report send time (Sunday evening proposed)? |
| 11. Parent dashboard | Should teachers approve each report, or only add optional notes? |
| 11. Parent dashboard | Languages for the report (English only, or Kannada/Hindi too)? |
| 12. Google Business Profile connector in the admin portal | Does a GBP listing already exist for the campus, and who owns it? |
| 12. Google Business Profile connector in the admin portal | Who approves review replies (School admin or marketing)? |
| 14. Social media and metrics dashboard for the group admin | Who owns each social account today (personal profiles must move to Business Manager)? |
| 14. Social media and metrics dashboard for the group admin | Is a scheduling tool wanted for the social team? |
| 15. Competitor deep study and gap report | Which local Bengaluru schools near Nagarbhavi does ULL lose families to? Add them to the study. |
| 15. Competitor deep study and gap report | Is ULL comfortable showing fee ranges publicly? |
| 16. Dedicated pages for ULL Global and ULL Auremont | ULL Global city and target opening year? |
| 16. Dedicated pages for ULL Global and ULL Auremont | Show Auremont fees publicly (range) or on request? |
| 16. Dedicated pages for ULL Global and ULL Auremont | Who signs off copy for each brand? |
| 17. Success metrics for each team | Seat target per grade for 2027-28? |
| 17. Success metrics for each team | Total marketing budget for the season, to set cost-per-admission targets? |
| 18. CRM lead source attribution (online, offline, coupons, WhatsApp) | Which telephony provider (or existing numbers) does the school use today? |
| 18. CRM lead source attribution (online, offline, coupons, WhatsApp) | Which school directories does ULL list on, and do they send leads by email or API? |
| 18. CRM lead source attribution (online, offline, coupons, WhatsApp) | Coupon benefits allowed for 2027-28? |
| 19. External CRM sync (Orggen CRM / Zoho CRM) | Orggen or Zoho first? Is one already in use with existing data? |
| 19. External CRM sync (Orggen CRM / Zoho CRM) | Zoho edition (affects API credits and custom modules)? |
| 19. External CRM sync (Orggen CRM / Zoho CRM) | Should external stage changes be accepted automatically? |
| 20. ULL India on aptitudetest.in (ullindia.aptitudetest.in) | When will the integration docs and sandbox be ready? |
| 20. ULL India on aptitudetest.in (ullindia.aptitudetest.in) | Which tests are free for enrolled students, and which are paid? |
| 20. ULL India on aptitudetest.in (ullindia.aptitudetest.in) | ULL's position on DMIT and MMPI. |
| 21. Audio recorder devices and AI success metrics per persona | How many devices in the pilot (counsellors, tele-callers)? |
| 21. Audio recorder devices and AI success metrics per persona | Do staff have company phones? |
| 21. Audio recorder devices and AI success metrics per persona | Union/staff policy considerations for teacher recordings? |
| 22. Sarvam AI voice agents (outbound and common inbound with human handover) | Existing phone numbers to keep, or new numbers? |
| 22. Sarvam AI voice agents (outbound and common inbound with human handover) | Fee reminders from the start of 2027-28, or earlier for the current year? |
| 22. Sarvam AI voice agents (outbound and common inbound with human handover) | Which voices (gender, accent) represent ULL best? Test with parents. |

# Appendix B. Glossary

| Term | Meaning |
| --- | --- |
| ACM / CloudFront / S3 / EC2 / RDS | AWS services for SSL certificates, content delivery, file storage, servers and managed databases |
| CDK | AWS Cloud Development Kit: the hosting setup written as code, so it can be rebuilt exactly |
| CDN | Content delivery network: serves images and files from locations close to the visitor |
| CMS | Content management system (Payload) used by the content team at /admin |
| CRM | Customer relationship management: the admissions system that tracks every family from enquiry to enrolment |
| VMS | Visitor management system: gate check-in, passes and live campus visitor status |
| SSO | Single sign-on: staff use their Microsoft work account; families use phone OTP or Google |
| Entra ID | Microsoft Entra ID (formerly Azure AD), Microsoft 365's sign-in service |
| OTP | One-time password sent by WhatsApp or SMS to verify a phone number |
| UTM | Tags added to links (source, medium, campaign) that show where a visitor came from |
| GBP | Google Business Profile: the school's listing on Google Search and Maps |
| GA4 / Search Console | Google Analytics 4 for website behaviour; Search Console for Google search performance |
| Core Web Vitals | Google's page speed and stability measures (LCP, CLS, INP) |
| JSON-LD / schema | Structured data that helps Google show rich results (school details, FAQs, events) |
| DPDP Act | Digital Personal Data Protection Act 2023, India's data protection law, including rules on children's data |
| DLT | TRAI's registration system for commercial SMS and calls in India |
| HPC | Holistic Progress Card under NEP 2020 / PARAKH for CBSE schools |
| IB, PYP, MYP, DP | International Baccalaureate and its Primary Years, Middle Years and Diploma programmes |
| PWA | Progressive web app: a website that can be installed on a phone and send notifications |
| STT / TTS | Speech-to-text and text-to-speech, used by recorders and voice agents |
| UAT | User acceptance testing environment (uat.ullindia.com), used before changes go to production |