## Read Me
ULL Auremont website — content map
Purpose | Page-by-page, section-by-section content plan for ullindia.com, laid out in the US school/university website format, mapped to the content we already have.
Source content | admissionportal/content/site-content.md (brand reference copy supplied by ULL). Vision, mission and values are ULL's own and are kept as written.
How to use | 1) Start with 'Gaps to Fill': it lists every item we still need, Launch items first. 2) Each page sheet shows every section in layout order. 3) When you supply an item, change its Status cell to Ready; the Sitemap counts update.
Status legend | Ready = we have the content (green). Partial = some content exists, needs a detail or approval (amber). Missing = needs to be written or supplied (red).
Owner column | School = ULL team provides it. Agency = we write or design it.
Example | Footer → Contact block → Missing → 'Full address with PIN, main phone, admissions phone/WhatsApp, email, office hours, Google Maps link'.
Prepared | 2026-10-20, draft v1 for review.
Ready
Partial
Missing

## Sitemap
ULL Auremont — sitemap and content readiness
Counts update automatically from each sheet's Status column.
Sheet | Pages | Sections | Ready | Partial | Missing | % Ready
Global | All pages | 11 | 3 | 4 | 4 | 27.27%
Home | Home | 15 | 9 | 2 | 4 | 60%
About | About Overview · Mission, Vision & Values · What Makes Us Unique · Leadership · Faculty · Accreditation & Affiliation · Brand Ambassador | 12 | 6 | 2 | 4 | 50%
Academics | Academics Overview · Learning Cycle · Foundational Stage · Preparatory Stage · Middle Stage · Secondary Stage · Assessment & Progress · Academic Calendar · Library & Reading · Results & Achievements | 13 | 10 | 0 | 3 | 76.92%
Student Life | Sports & Fitness · Pulse · Ruchi · Kushala · Aurora Lab & Robotics · Summit Pathway · Clubs & Events | 12 | 9 | 2 | 1 | 75%
Admissions | Admissions Overview · Admission Process · Key Dates · Fees & Scholarships · Visit Us · Enquire · Apply Online · Admissions FAQ · Admissions Contact | 13 | 2 | 5 | 6 | 15.38%
Campus | Campus Overview · Facilities · Campus Tour · Gallery · Safety & Security · Health & Wellbeing · Transport · Meals · Location | 9 | 0 | 2 | 7 | 0%
Parents | Parents Overview · School Day · Uniform · Policies · Calendar & Circulars · Parent Portal | 7 | 3 | 0 | 4 | 42.86%
News & Events | News · Events · Blog / Parent Resources | 3 | 0 | 0 | 3 | 0%
Contact & Careers | Contact · Careers · Alumni | 4 | 1 | 1 | 2 | 25%
Legal & Compliance | Mandatory Public Disclosure · Privacy Policy · Terms of Use · Child Safeguarding · Accessibility · Image disclaimer | 6 | 2 | 0 | 4 | 33.33%
Portal | Register / Login · Dashboard · Add Child · Application · Documents · Application Status · Messages · Visitor Pass | 8 | 3 | 2 | 3 | 37.5%
Total |  | 113 | 48 | 20 | 45 | 42.48%

## Gaps to Fill
Content gaps to fill (Missing first, then Partial)
Snapshot when this file was made. Update Status on the page sheets as items arrive.
# | Priority | Sheet | Page | Section | What you need to provide | Images / assets | Status
1 | Launch | Global | All pages | Contact block | Full address with PIN, main phone, admissions phone/WhatsApp, email, office hours, Google Maps link | — | Missing
2 | Launch | Global | All pages | Social links | Official social media handles/URLs | — | Missing
3 | Launch | Global | All pages | Affiliation line | CBSE affiliation number and school code (or 'affiliation applied' status) | — | Missing
4 | Launch | Global | All pages | WhatsApp button | WATI WhatsApp business number | — | Missing
5 | Launch | Home | Home | Key facts strip | Numbers: years serving Nagarbhavi, student count, student–teacher ratio, class size, campus size, number of sports/clubs | Icons (we design) | Missing
6 | Launch | Home | Home | Principal's welcome | Principal's name, photo and welcome message | Principal portrait | Missing
7 | Launch | Home | Home | Parent testimonials | 3–5 parent testimonials with consent (or skip until first term) | Parent photos (optional) | Missing
8 | Launch | Home | Home | Photo strip | Real campus/children photos (consent-cleared) | Photos | Missing
9 | Launch | About | About Overview | Our story / history | Story: when ULL started in Nagarbhavi, milestones, why the renewal, founders | Archive/founding photos | Missing
10 | Launch | About | Leadership | Principal's message | Principal's full message (250–400 words), name, qualifications | Principal portrait | Missing
11 | Launch | About | Leadership | Management / governing body | Names, roles and photos of trustees/management (ULL leadership) | Portraits | Missing
12 | Launch | About | Faculty | Faculty directory | Faculty list with subjects and qualifications (photos optional) | Teacher photos | Missing
13 | Launch | Admissions | Admission Process | Eligibility & age criteria | Age criteria per grade (as on 1 June / 31 March), eligibility for lateral entry | — | Missing
14 | Launch | Admissions | Admission Process | Documents required | Document list (birth certificate, TC, report card, Aadhaar, photos, address proof, etc.) | — | Missing
15 | Launch | Admissions | Key Dates | Admission timeline | Admission calendar dates | — | Missing
16 | Launch | Admissions | Fees & Scholarships | Fee structure | Decide: publish fee table per grade, or 'fees shared at visit'. Transport/meal fees | Fee PDF | Missing
17 | Launch | Admissions | Fees & Scholarships | Scholarships / sibling concession | Scholarship, sibling or merit concession policy (or 'none') | — | Missing
18 | Launch | Admissions | Admissions Contact | Admissions team | Admissions counsellor name(s), direct phone/WhatsApp, hours | Counsellor photo | Missing
19 | Launch | Contact & Careers | Contact | Contact details + map | All contact details (see Global → Contact block) | — | Missing
20 | Launch | Legal & Compliance | Mandatory Public Disclosure | CBSE disclosure | All CBSE Appendix-IX data and documents (affiliation letter, NOC, building safety, fire, water, etc.) | PDF documents | Missing
21 | Launch | Legal & Compliance | Privacy Policy | Privacy policy | Approve draft we prepare; name of grievance officer/contact | — | Missing
22 | Launch | Legal & Compliance | Terms of Use | Website terms | Approve draft we prepare | — | Missing
23 | Launch | Legal & Compliance | Child Safeguarding | Safeguarding/POCSO policy | Policy text and contact person | — | Missing
24 | Launch | Global | All pages | Logo + main navigation | High-resolution logo file (SVG or PNG, transparent background); approve final menu names | Logo SVG/PNG | Partial
25 | Launch | Campus | Location | Map + directions | Exact address, landmarks, parking info | — | Partial
26 | Phase 2 | Academics | Academic Calendar | Year calendar | Academic year calendar (term dates, holidays, exam windows, PTMs, Term Showcase dates) | PDF calendar | Missing
27 | Phase 2 | Academics | Library & Reading | Library programme | Library details: size, timings, reading programme | Library photo | Missing
28 | Phase 2 | Academics | Results & Achievements | Board results, olympiads, awards | Past Grade 10 results (if any), olympiad/competition wins; or hide until first results | — | Missing
29 | Phase 2 | Student Life | Sports & Fitness | Houses | House names, colours and mascots | House crests | Missing
30 | Phase 2 | Campus | Facilities | Facility list | Confirmed facility list with 2–3 lines each | Photo per facility | Missing
31 | Phase 2 | Campus | Campus Tour | Virtual tour | Real photos or walk-through video; label any concept images clearly | Photos/video | Missing
32 | Phase 2 | Campus | Gallery | Filterable gallery | Real photo sets per category with consent | Photos | Missing
33 | Phase 2 | Campus | Safety & Security | Safety page | Safety measures, CCTV, gate/visitor policy, staff background checks, POCSO committee, fire drills | — | Missing
34 | Phase 2 | Campus | Health & Wellbeing | Infirmary + counsellor | Infirmary staffing, school counsellor, health check-ups | — | Missing
35 | Phase 2 | Campus | Transport | Bus routes | Routes/areas covered, safety features, transport fee approach | Bus photo | Missing
36 | Phase 2 | Campus | Meals | Food programme | Is lunch provided? Menu sample, veg/non-veg policy | Dining photo | Missing
37 | Phase 2 | Parents | School Day | Timings | School timings per stage, Saturday policy, after-school options | — | Missing
38 | Phase 2 | Parents | Uniform | Uniform guide | Uniform details, where to buy, sports uniform | Uniform photos | Missing
39 | Phase 2 | Parents | Policies | Key policies | Attendance, homework, mobile/device, discipline, leave and fee-payment policies | PDFs | Missing
40 | Phase 2 | Parents | Calendar & Circulars | Calendar + circulars | Calendar (shared with Academics) and circular format | — | Missing
41 | Phase 2 | News & Events | News | News list + article template | 3–5 launch articles (Auremont launch, Jonty Rhodes, admissions open, campus renewal) | Article photos | Missing
42 | Phase 2 | News & Events | Events | Events calendar + event page | Upcoming events: Open House, Term Showcase, Sports Meet dates | Event images | Missing
43 | Phase 2 | News & Events | Blog / Parent Resources | Articles for SEO | Topics list + author (e.g. choosing a CBSE school, NEP 2020 explained, early years) | — | Missing
44 | Phase 2 | Portal | Application | Application form | Final application form fields and declaration text from school | Sample paper form (if any) | Missing
45 | Phase 2 | Portal | Documents | Document upload | Document list (same as Admissions → Documents) | — | Missing
46 | Phase 2 | Portal | Messages | Message templates | Approve message wording; WATI/Gupshup template approvals; sender ID | — | Missing
47 | Phase 2 | Global | All pages | Quick links + legal | Approve; legal pages content needed (see Legal sheet) | — | Partial
48 | Phase 2 | Global | All pages | Group line | Confirm group name usage and link to ullindia.com group page | ULL group logo | Partial
49 | Phase 2 | Global | All pages | Site-wide SEO | Favicon, share image (1200×630), Google Business Profile link, target keywords list (e.g. 'CBSE school Nagarbhavi') | Favicon, OG image | Partial
50 | Phase 2 | Home | Home | Ambassador feature | Approved Jonty Rhodes quote and usage rights for his photo | Licensed ambassador photo | Partial
51 | Phase 2 | Home | Home | Latest news + upcoming events | 2–3 starter news items and upcoming dates (Open House, Admissions) | Event photos | Partial
52 | Phase 2 | About | Accreditation & Affiliation | CBSE affiliation, NCF/NEP alignment | Affiliation number, school code, validity, any memberships/awards | Certificates (scans) | Partial
53 | Phase 2 | About | Brand Ambassador | Ambassador story | Short bio + quote + what he will do with students | Licensed photos/video | Partial
54 | Phase 2 | Student Life | Sports & Fitness | Sports offered + facilities | Confirm actual sports facilities and coaches (names/credentials) | Facility photos | Partial
55 | Phase 2 | Student Life | Clubs & Events | Annual events | Annual Day, field trips, festivals celebrated, competitions list | Event photos | Partial
56 | Phase 2 | Admissions | Admissions Overview | Admissions open banner | Admission year (e.g. 2027–28) | Family/counselling photo | Partial
57 | Phase 2 | Admissions | Admission Process | 5 steps | Admissions phone number (step 1 says [phone]) | Step icons (we design) | Partial
58 | Phase 2 | Admissions | Visit Us | Book a campus visit | Visit days and time slots, max visits per slot | Campus photo | Partial
59 | Phase 2 | Admissions | Apply Online | Apply now → portal | Application form fields (see Portal sheet) | — | Partial
60 | Phase 2 | Admissions | Admissions FAQ | FAQs (FAQPage schema) | Fill [number] years in 'Is it a new school?'; add FAQs on fees, transport, timings, uniform, meals, age criteria | — | Partial
61 | Phase 2 | Campus | Campus Overview | Campus intro | Campus size, buildings, one-paragraph description | Aerial/exterior photo | Partial
62 | Phase 2 | Contact & Careers | Careers | Why work with us + openings | Open positions, HR email, application process | Staff photo | Partial
63 | Phase 2 | Portal | Add Child | Child profile | Confirm required fields | — | Partial
64 | Phase 2 | Portal | Visitor Pass | QR visitor pass + front desk | Front desk staff list, hosts to notify, visitor ID policy | — | Partial
65 | Optional | Contact & Careers | Alumni | Alumni network | Optional: alumni stories of ULL; can skip at launch | — | Missing

## Global
Global — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | All pages | — | Utility bar | Quick links | US pattern: Apply · Visit · Enquire · Parent Login always one click away | site-content.md: Concept CTAs: Book a campus visit, Enquire now, Apply now | Ready | Confirm labels: Apply / Book a Visit / Enquire / Parent Login | — | Agency
2 | All pages | — | Header | Logo + main navigation | Logo left, 8 menus, sticky on scroll, mobile menu | site-content.md: Concept nav: Our approach, Academics, School life, Gallery, Campus tour, For parents, Plan a visit | Partial | High-resolution logo file (SVG or PNG, transparent background); approve final menu names | Logo SVG/PNG | School
3 | All pages | — | Header | Announcement strip | Optional one-line notice (admissions open, events) | site-content.md: 'Admissions open for Nursery to Grade 10' | Ready | Admissions year to show (e.g. 2027–28) | — | Agency
4 | All pages | — | Footer | Brand block | Logo, tagline, motto | site-content.md: Tagline + motto in Brand essentials | Ready | — | Logo (light version for dark footer) | Agency
5 | All pages | — | Footer | Contact block | Address, phone, email, office hours, map link | Contact line has [address], [PIN], [phone], [email] placeholders | Missing | Full address with PIN, main phone, admissions phone/WhatsApp, email, office hours, Google Maps link | — | School
6 | All pages | — | Footer | Quick links + legal | Sitemap links, Privacy, Terms, Mandatory Disclosure, Accessibility | — | Partial | Approve; legal pages content needed (see Legal sheet) | — | School
7 | All pages | — | Footer | Social links | Instagram, Facebook, YouTube, LinkedIn | — | Missing | Official social media handles/URLs | — | School
8 | All pages | — | Footer | Affiliation line | 'Affiliated to CBSE, New Delhi · Affiliation No. ____ · School Code ____' | CBSE stated, no numbers | Missing | CBSE affiliation number and school code (or 'affiliation applied' status) | — | School
9 | All pages | — | Footer | Group line | 'A United Learning League (ULL) school' | site-content.md: Concept footer: United Learning League | Partial | Confirm group name usage and link to ullindia.com group page | ULL group logo | School
10 | All pages | — | SEO | Site-wide SEO | Title pattern, meta descriptions, Open Graph image, favicon, JSON-LD School schema, Google Business Profile | site-content.md: Meta description in concept HTML | Partial | Favicon, share image (1200×630), Google Business Profile link, target keywords list (e.g. 'CBSE school Nagarbhavi') | Favicon, OG image | School
11 | All pages | — | Chat/Contact | WhatsApp button | Floating WhatsApp (WATI) button | — | Missing | WATI WhatsApp business number | — | School

## Home
Home — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Home | / | Hero | Headline + sub + CTAs | Big image/video, headline, 2 CTAs | site-content.md: 'Every lesson connects. Every child rises.' / 'Great habits. Extraordinary possibilities.' + Book a visit / Enquire | Ready | Pick one headline (content vs concept differ) | Hero photo or 20–30s campus video (real, not AI) | Agency
2 | Home | / | Hero | Ambassador feature | Brand ambassador badge + quote | site-content.md: Jonty Rhodes · Brand Ambassador | Partial | Approved Jonty Rhodes quote and usage rights for his photo | Licensed ambassador photo | School
3 | Home | / | Intro | Welcome statement | One paragraph: who we are, where, grades | site-content.md: 'Welcome to ULL Auremont, a CBSE school in Nagarbhavi…' + 'The schooling you wish you'd had' | Ready | — | — | Agency
4 | Home | / | At a glance | Key facts strip | US standard: 4–6 numbers (years, students, ratio, acres, sports, clubs) | Not present | Missing | Numbers: years serving Nagarbhavi, student count, student–teacher ratio, class size, campus size, number of sports/clubs | Icons (we design) | School
5 | Home | / | Pillars | Four pillars | 4 cards linking to pages | site-content.md: Four pillars text | Ready | — | 4 pillar images | Agency
6 | Home | / | Programme | Academics teaser | Learning Cycle summary + link | site-content.md: Academics teaser | Ready | — | Classroom photo | Agency
7 | Home | / | Programme | Sports teaser | Sports summary + link | site-content.md: Sports & Fitness teaser | Ready | — | Sports photo | Agency
8 | Home | / | Programme | Beyond the Classroom teaser | Pulse · Ruchi · Kushala · Aurora Lab · Summit | site-content.md: Teaser list | Ready | — | Activity photo | Agency
9 | Home | / | Values | Vision + mission | Short block | site-content.md: Our vision / Our mission | Ready | — | — | Agency
10 | Home | / | Leadership | Principal's welcome | US standard: photo + 80-word message + link | Not present | Missing | Principal's name, photo and welcome message | Principal portrait | School
11 | Home | / | Social proof | Parent testimonials | 3 quotes with name and grade | Not present | Missing | 3–5 parent testimonials with consent (or skip until first term) | Parent photos (optional) | School
12 | Home | / | News & events | Latest news + upcoming events | Pulls from News/Events CMS | Not present | Partial | 2–3 starter news items and upcoming dates (Open House, Admissions) | Event photos | School
13 | Home | / | Gallery | Photo strip | 3–6 photos linking to gallery | Concept uses AI visualisations | Missing | Real campus/children photos (consent-cleared) | Photos | School
14 | Home | / | FAQ teaser | 3 top questions | Links to Admissions FAQ | site-content.md: FAQ list | Ready | — | — | Agency
15 | Home | / | CTA band | Book a campus visit | Form link + phone | site-content.md: 'Ready to see it for yourself?' | Ready | — | Background photo | Agency

## About
About — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | About Overview | /about | Hero | Page intro | Title, short intro, photo | site-content.md: Brand essentials + name meaning | Ready | — | Campus exterior photo | Agency
2 | About Overview | /about | Content | Our story / history | US standard: founding year, journey, renewal as Auremont | 'Our story — To be filled in' | Missing | Story: when ULL started in Nagarbhavi, milestones, why the renewal, founders | Archive/founding photos | School
3 | About Overview | /about | Content | The name Auremont | Meaning of the name | site-content.md: The name: Auremont | Ready | — | — | Agency
4 | Mission, Vision & Values | /about/mission | Content | Motto, vision, mission | Statement blocks | site-content.md: Our motto / vision / mission | Ready | — | — | Agency
5 | Mission, Vision & Values | /about/mission | Content | The Auremont Way | 5 values with one-liners | site-content.md: Our values: the Auremont Way | Ready | — | Value icons (we design) | Agency
6 | What Makes Us Unique | /about/why-auremont | Content | 9 differentiators | Card list | site-content.md: About Us: What makes us unique | Ready | — | — | Agency
7 | Leadership | /about/leadership | Content | Principal's message | Photo + full message + signature | Not present | Missing | Principal's full message (250–400 words), name, qualifications | Principal portrait | School
8 | Leadership | /about/leadership | Content | Management / governing body | US standard: board/trustees list | Not present | Missing | Names, roles and photos of trustees/management (ULL leadership) | Portraits | School
9 | Faculty | /about/faculty | Content | Teaching approach | How we support teachers, quality | site-content.md: About Us: Our teachers | Ready | — | — | Agency
10 | Faculty | /about/faculty | Content | Faculty directory | Name, subject, qualification, photo | '[Introduction to the principal and faculty… to be added.]' | Missing | Faculty list with subjects and qualifications (photos optional) | Teacher photos | School
11 | Accreditation & Affiliation | /about/accreditation | Content | CBSE affiliation, NCF/NEP alignment | US standard: accreditation page | site-content.md: CBSE + NCF 2023 mentioned | Partial | Affiliation number, school code, validity, any memberships/awards | Certificates (scans) | School
12 | Brand Ambassador | /about/jonty-rhodes | Content | Ambassador story | Why Jonty Rhodes, his association | site-content.md: Concept hero only | Partial | Short bio + quote + what he will do with students | Licensed photos/video | School

## Academics
Academics — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Academics Overview | /academics | Hero | Intro | 'Children understand before they memorise…' | site-content.md: Academics: Our approach | Ready | — | Classroom photo | Agency
2 | Academics Overview | /academics | Content | What we believe | 6 beliefs | site-content.md: What we believe | Ready | — | — | Agency
3 | Academics Overview | /academics | Content | Curriculum & framework | CBSE + NCF 2023, four stages | site-content.md: Our approach | Ready | — | — | Agency
4 | Learning Cycle | /academics/learning-cycle | Content | 5 steps table | Connect, Experience, Clarify, Apply, Reflect | site-content.md: The Auremont Learning Cycle | Ready | — | Step diagram (we design) | Agency
5 | Learning Cycle | /academics/learning-cycle | Content | Indian roots + classroom look-fors | Lens not a subject; what you'll see | site-content.md: Indian roots / In every classroom / Every learner | Ready | — | — | Agency
6 | Foundational Stage | /academics/foundational | Content | Nursery–Grade 2 full page | Areas, what they learn, a day, outcomes, Indian roots, progress | site-content.md: Academics: Foundational Stage | Ready | Confirm entry ages for Nursery, LKG, UKG | Early-years photos | Agency
7 | Preparatory Stage | /academics/preparatory | Content | Grades 3–5 full page | Subjects table, classroom, outcomes, roots, progress | site-content.md: Academics: Preparatory Stage | Ready | — | Photos | Agency
8 | Middle Stage | /academics/middle | Content | Grades 6–8 full page | Subjects table, classroom, outcomes, roots, progress | site-content.md: Academics: Middle Stage | Ready | — | Photos | Agency
9 | Secondary Stage | /academics/secondary | Content | Grades 9–10 full page | Subjects, board prep, outcomes, beyond the exam | site-content.md: Academics: Secondary Stage | Ready | Confirm the CBSE skill subject offered | Photos | Agency
10 | Assessment & Progress | /academics/assessment | Content | Assessment by stage + report card | Table + whole-child report | site-content.md: Academics: Assessment and progress | Ready | — | Sample report card (optional) | Agency
11 | Academic Calendar | /academics/calendar | Content | Year calendar | US standard: term dates, holidays, exams, PTMs | Not present | Missing | Academic year calendar (term dates, holidays, exam windows, PTMs, Term Showcase dates) | PDF calendar | School
12 | Library & Reading | /academics/library | Content | Library programme | US standard: library page | Only 'reading corners' mentioned | Missing | Library details: size, timings, reading programme | Library photo | School
13 | Results & Achievements | /academics/results | Content | Board results, olympiads, awards | US standard: outcomes page | Not present | Missing | Past Grade 10 results (if any), olympiad/competition wins; or hide until first results | — | School

## Student Life
Student Life — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Sports & Fitness | /student-life/sports | Hero | Intro | 'Fit body. Sharp mind. Strong character.' | site-content.md: Sports & Fitness | Ready | — | Action sports photo | Agency
2 | Sports & Fitness | /student-life/sports | Content | Sports promise | Plays, measured, competes, excels | site-content.md: Our sports promise | Ready | — | — | Agency
3 | Sports & Fitness | /student-life/sports | Content | Programme by stage | Table by stage | site-content.md: A programme that grows with your child | Ready | — | — | Agency
4 | Sports & Fitness | /student-life/sports | Content | Sports offered + facilities | 11 sports + where they're played | site-content.md: Sports list; courtyard concept (2 badminton, 1 volleyball) | Partial | Confirm actual sports facilities and coaches (names/credentials) | Facility photos | School
5 | Sports & Fitness | /student-life/sports | Content | Houses | US standard: house names/colours | Houses mentioned, not named | Missing | House names, colours and mascots | House crests | School
6 | Sports & Fitness | /student-life/sports | Content | Sports calendar + Indian roots | Events and traditional games | site-content.md: The sports calendar / Indian roots on the field | Ready | — | — | Agency
7 | Pulse | /student-life/pulse | Content | Weekly skill programme | Skill families, examples, monthly theme | site-content.md: Pulse: the heart of our week | Ready | — | Photos | Agency
8 | Ruchi | /student-life/ruchi | Content | Hobby hour | Hobby groups by type | site-content.md: Ruchi: hobby hour | Ready | Confirm which hobbies run in year 1 | Photos | Agency
9 | Kushala | /student-life/kushala | Content | Life skills | Monthly skill, examples | site-content.md: Kushala: life skills | Ready | — | Sample practice card | Agency
10 | Aurora Lab & Robotics | /student-life/aurora-lab | Content | Science lab, robotics, computing | 3 blocks | site-content.md: Aurora Lab, robotics and computing | Ready | — | Lab photos | Agency
11 | Summit Pathway | /student-life/summit | Content | Olympiads, debate, careers | Programme detail | site-content.md: Summit Pathway | Ready | — | — | Agency
12 | Clubs & Events | /student-life/events | Content | Annual events | US standard: Annual Day, Sports Meet, Showcases, trips | site-content.md: Term Showcase, Sports Meet, Fitness Week | Partial | Annual Day, field trips, festivals celebrated, competitions list | Event photos | School

## Admissions
Admissions — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Admissions Overview | /admissions | Hero | Admissions open banner | Year, grades, CTA | site-content.md: 'Admissions open, Nursery to Grade 10.' | Partial | Admission year (e.g. 2027–28) | Family/counselling photo | School
2 | Admissions Overview | /admissions | Content | Why choose Auremont | Short reasons + link | site-content.md: What makes us unique | Ready | — | — | Agency
3 | Admission Process | /admissions/process | Content | 5 steps | Enquire, Visit, Meet, Confirm, Orientation | site-content.md: Admissions steps 1–5 | Partial | Admissions phone number (step 1 says [phone]) | Step icons (we design) | School
4 | Admission Process | /admissions/process | Content | Eligibility & age criteria | US standard: age cut-off per grade | Not present | Missing | Age criteria per grade (as on 1 June / 31 March), eligibility for lateral entry | — | School
5 | Admission Process | /admissions/process | Content | Documents required | Checklist | 'complete documents' only | Missing | Document list (birth certificate, TC, report card, Aadhaar, photos, address proof, etc.) | — | School
6 | Key Dates | /admissions/dates | Content | Admission timeline | Open, visit days, interaction, offers, orientation | Not present | Missing | Admission calendar dates | — | School
7 | Fees & Scholarships | /admissions/fees | Content | Fee structure | US standard: tuition page (or 'contact us' note) | Not present | Missing | Decide: publish fee table per grade, or 'fees shared at visit'. Transport/meal fees | Fee PDF | School
8 | Fees & Scholarships | /admissions/fees | Content | Scholarships / sibling concession | Policy summary | Not present | Missing | Scholarship, sibling or merit concession policy (or 'none') | — | School
9 | Visit Us | /admissions/visit | Form | Book a campus visit | Visit form → Admissions Desk; slot picker | site-content.md: Enquiry form fields + preferred visit date | Partial | Visit days and time slots, max visits per slot | Campus photo | School
10 | Enquire | /admissions/enquire | Form | Enquiry form | Parent name, phone, email, child's name, grade, current school, visit date, family priority | site-content.md: Enquiry form (concept adds 'Family priority') | Ready | Confirm 'Family priority' options and add 'How did you hear about us?' options | — | Agency
11 | Apply Online | /apply | Portal | Apply now → portal | Register once, apply per child | Not present (new) | Partial | Application form fields (see Portal sheet) | — | School
12 | Admissions FAQ | /admissions/faq | Content | FAQs (FAQPage schema) | 11+ Q&As | site-content.md: Frequently asked questions (11 Qs) | Partial | Fill [number] years in 'Is it a new school?'; add FAQs on fees, transport, timings, uniform, meals, age criteria | — | School
13 | Admissions Contact | /admissions/contact | Content | Admissions team | Counsellor name, phone, WhatsApp, hours | Not present | Missing | Admissions counsellor name(s), direct phone/WhatsApp, hours | Counsellor photo | School

## Campus
Campus — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Campus Overview | /campus | Hero | Campus intro | Summary + map | site-content.md: 'Facilities · Gallery · Transport' | Partial | Campus size, buildings, one-paragraph description | Aerial/exterior photo | School
2 | Facilities | /campus/facilities | Content | Facility list | Classrooms, Aurora Lab, science, computer & robotics lab, library, sports, art/music/dance rooms, infirmary | '[To be completed once the facility list is confirmed…]' | Missing | Confirmed facility list with 2–3 lines each | Photo per facility | School
3 | Campus Tour | /campus/tour | Content | Virtual tour | Slide tour or 360°/video | Concept tour slides (AI visualisations) | Missing | Real photos or walk-through video; label any concept images clearly | Photos/video | School
4 | Gallery | /campus/gallery | Content | Filterable gallery | Categories: classrooms, sport, arts, events | Concept gallery with filters (AI images) | Missing | Real photo sets per category with consent | Photos | School
5 | Safety & Security | /campus/safety | Content | Safety page | US standard: CCTV, visitor management, staff checks, POCSO, fire safety | Not present | Missing | Safety measures, CCTV, gate/visitor policy, staff background checks, POCSO committee, fire drills | — | School
6 | Health & Wellbeing | /campus/health | Content | Infirmary + counsellor | Nurse, doctor on call, counsellor | 'infirmary' suggested only | Missing | Infirmary staffing, school counsellor, health check-ups | — | School
7 | Transport | /campus/transport | Content | Bus routes | Routes, GPS, attendants, fees | 'Transport' heading only | Missing | Routes/areas covered, safety features, transport fee approach | Bus photo | School
8 | Meals | /campus/meals | Content | Food programme | Menu, kitchen, dietary policy | Concept image 'kitchen-dining-space' | Missing | Is lunch provided? Menu sample, veg/non-veg policy | Dining photo | School
9 | Location | /campus/location | Content | Map + directions | Google Map embed, landmarks | site-content.md: Nagarbhavi, Bengaluru | Partial | Exact address, landmarks, parking info | — | School

## Parents
Parents — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Parents Overview | /parents | Content | Partnering with parents | Pulse notes, Kushala cards, showcase, fitness card, PTMs | site-content.md: Parents: Partnering with parents | Ready | — | Parent photo | Agency
2 | Parents Overview | /parents | Content | A week at ULL Auremont | Day-by-day story | site-content.md: A week at ULL Auremont (Anika) | Ready | — | Illustrations/photos | Agency
3 | School Day | /parents/school-day | Content | Timings | US standard: daily schedule by stage | Not present | Missing | School timings per stage, Saturday policy, after-school options | — | School
4 | Uniform | /parents/uniform | Content | Uniform guide | Uniform per stage, supplier | Concept mentions proposed navy uniform | Missing | Uniform details, where to buy, sports uniform | Uniform photos | School
5 | Policies | /parents/policies | Content | Key policies | Attendance, homework, devices, behaviour, leave | Not present | Missing | Attendance, homework, mobile/device, discipline, leave and fee-payment policies | PDFs | School
6 | Calendar & Circulars | /parents/calendar | Content | Calendar + circulars | Links to calendar, monthly Pulse notes | Not present | Missing | Calendar (shared with Academics) and circular format | — | School
7 | Parent Portal | /portal | Portal | Login entry | Login / register link and what parents can do | Not present (new) | Ready | — | — | Agency

## News & Events
News & Events — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | News | /news | Listing | News list + article template | Title, date, image, body, tags | Not present | Missing | 3–5 launch articles (Auremont launch, Jonty Rhodes, admissions open, campus renewal) | Article photos | School
2 | Events | /events | Listing | Events calendar + event page | Date, time, venue, register button | Not present | Missing | Upcoming events: Open House, Term Showcase, Sports Meet dates | Event images | School
3 | Blog / Parent Resources | /resources | Listing | Articles for SEO | US standard: thought-leadership; drives Google traffic | Not present | Missing | Topics list + author (e.g. choosing a CBSE school, NEP 2020 explained, early years) | — | School

## Contact & Careers
Contact & Careers — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Contact | /contact | Content | Contact details + map | Address, phones, email, hours, map, form | Placeholders only | Missing | All contact details (see Global → Contact block) | — | School
2 | Contact | /contact | Form | General enquiry form | Name, phone, email, topic, message | Not present (new) | Ready | — | — | Agency
3 | Careers | /careers | Content | Why work with us + openings | US standard: careers page, job listings | site-content.md: Teacher-support text in Our teachers | Partial | Open positions, HR email, application process | Staff photo | School
4 | Alumni | /alumni | Content | Alumni network | US standard (optional for launch) | Not present | Missing | Optional: alumni stories of ULL; can skip at launch | — | School

## Legal & Compliance
Legal & Compliance — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Mandatory Public Disclosure | /mandatory-disclosure | Content | CBSE disclosure | Required by CBSE: affiliation, trust, infrastructure, staff, results, fee, SMC, PTA | Not present | Missing | All CBSE Appendix-IX data and documents (affiliation letter, NOC, building safety, fire, water, etc.) | PDF documents | School
2 | Privacy Policy | /privacy | Content | Privacy policy | How enquiry/portal/visitor data is used (DPDP Act 2023) | Not present | Missing | Approve draft we prepare; name of grievance officer/contact | — | School
3 | Terms of Use | /terms | Content | Website terms | Standard terms | Not present | Missing | Approve draft we prepare | — | School
4 | Child Safeguarding | /safeguarding | Content | Safeguarding/POCSO policy | US standard: child protection statement | Not present | Missing | Policy text and contact person | — | School
5 | Accessibility | /accessibility | Content | Accessibility statement | WCAG commitment | Not present | Ready | We draft; approve | — | Agency
6 | Image disclaimer | (gallery) | Content | Concept image note | Label AI visualisations until real photos | site-content.md: 'Campus design visualisations · AI-generated imagery' | Ready | Remove once real photos are in | — | Agency

## Portal
Portal — content map
Rows shaded red = Missing, amber = Partial, green = Ready. Fill the 'What you need to provide' items, then set Status to Ready.
# | Page | URL | Layout block | Section | What goes here (US standard) | Content we have (source) | Status | What you need to provide | Images / assets | Owner | Notes
1 | Register / Login | /portal/login | Form | Parent registration | Name, mobile (OTP), email, password; register once | Not present (new) | Ready | Confirm login by mobile OTP + email | — | Agency
2 | Dashboard | /portal | Portal | Family dashboard | Children, applications, visit bookings, messages | Not present (new) | Ready | — | — | Agency
3 | Add Child | /portal/children | Form | Child profile | Name, DOB, gender, current school, grade, photo | Not present (new) | Partial | Confirm required fields | — | School
4 | Application | /portal/apply | Form | Application form | Child + parent details, address, previous school, sibling, medical/special needs, declaration | Not present (new) | Missing | Final application form fields and declaration text from school | Sample paper form (if any) | School
5 | Documents | /portal/documents | Form | Document upload | Upload per required document | Not present (new) | Missing | Document list (same as Admissions → Documents) | — | School
6 | Application Status | /portal/status | Portal | Status tracker | Enquired → Visit booked → Visited → Interaction → Documents → Confirmed → Orientation | site-content.md: Admissions 5 steps | Ready | Confirm stage names parents should see | — | Agency
7 | Messages | /portal/messages | Portal | Message templates | Email (SES), SMS (Gupshup), WhatsApp (WATI) per stage | Not present (new) | Missing | Approve message wording; WATI/Gupshup template approvals; sender ID | — | School
8 | Visitor Pass | (VMS) | Portal | QR visitor pass + front desk | Pass email/WhatsApp, check-in screen, host alert | Not present (new) | Partial | Front desk staff list, hosts to notify, visitor ID policy | — | School